## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Quotation for new service connection at Salkumarhat TW No-III, Application No- 4002994687 |  |  | BILL/00001/2022-2023 |  | 21/11/2022 | 21/11/2022 | WBSEDCL | 1.42 | 0 | 0 | 0
2 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Quotation for new service connection at SALKUMAR HAT, P/H no. III, Application no. 4002994687 |  |  | VCH/001470/2022-2023 | BP-93/22-23 | 22/11/2022 | 22/11/2022 | WBSEDCL | 1.42 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Laying Distribution line of UPVC & Di Pipe , with providing FHTC Connection for the Salkumarhat Water Supply Scheme Under Alipurduar Division PHE DTE (PART-A) | Alipurduar RWS | Birpara Sub Division | ORD/000131/2021-2022 | 1242/ALD | 27/09/2021 | 26/11/2021 | KAMALESH ROY | 25.25 | 4.65 | 18.43 | 9
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Repairing & renovation of Pump House, Pathway, Boundary wall (2nd site) & laying DI Pipe line at Salkumarhat WSS under Alipurduar Division PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000099/2021-2022 | 898/ALD | 03/09/2021 | 18/10/2021 | TAPASH DAS | 4.82 | 0 | 0 | 62
5 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR MUNSHIPARA P/H NO.III |  |  | BILL/00681/2023-2024 |  | 06/06/2023 | 06/06/2023 | WBSEDCL | 1 | 0 | 0 | 0
6 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR SALKUMARHAT P/H NO.IV |  |  | BILL/00680/2023-2024 | BP-2023-24-194 | 22/06/2023 | 22/06/2023 | WBSEDCL | 1.48 | 0 | 0 | 0
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Cons. Of Rising line, pathway, surface drain, laying of DI and UPVC pipeline and restoration of FHTC at Salkumarhat PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division,JUNIOR ENGINEER | ORD/000222/2023-2024 | 1582/ALD | 24/08/2023 | 22/11/2023 | TAPASH DAS | 18.46 | 0 | 0 | 5
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Salkumarhat PWSS, Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division,RWS Madarihat - Birpara Block | ORD/000479/2021-2022 | 2898/ALD | 08/03/2022 | 18/12/2025 | DILIP MAHATO | 48.52 | 0 | 0 | 65
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at 4th site for SALKUMARHAT PWSS Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000067/2022-2023 | 339/ALD | 02/05/2022 | 06/01/2025 | SHYAMAL ROY | 24.17 | 9.7 | 40.13 | 100
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Laying of pipeline distribution system (Parallel and left out Area) and other allied works at Salkumarhat PWSS within APD-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000104/2025-2026 | 1222/ALD | 01/07/2025 | 30/08/2025 | DILIP MAHATO (OPC) PRIVATE LIMITED | 53.57 | 0 | 0 | 0
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Reparing of Pump House at 2nd site of SALKUMARHAT PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000570/2024-2025 | 5385/ALD | 17/03/2025 | 16/05/2025 | TAPASH DAS | 0.79 | 0 | 0 | 0
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Providing balance FHTC and construction of new sluice valve chamber for controlling water including laying UPVC pipe at leftout area of Chhoto Salkumar PWSS and other allied works adjacent to Augmentation of Salkumarhat PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000103/2025-2026 | 1188/ALD | 26/06/2025 | 24/09/2025 | M/S DUTTA AND CO | 26.37 | 0 | 0 | 0
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Reparing of Pump House at HEADWORK site of SALKUMARHAT PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000576/2024-2025 | 5390/ALD | 17/03/2025 | 16/05/2025 | TAPASH DAS | 0.94 | 0 | 0 | 0
15 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Painting of Old OHR (350 cum) at Chhoto Salkumar adjacent to Augmentation of Salkumarhat PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000198/2025-2026 | 2105/ALD | 23/09/2025 | 22/11/2025 | NARENDRA BHADANI. | 3.04 | 0 | 0 | 0
16 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Repairing of Pump house at 3rd site of Chhoto Salkumar adjacent to Augmentation of Salkumarhat PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000159/2025-2026 | 1744/ALD | 13/08/2025 | 12/10/2025 | ANIRBAN DEY SARKAR CONSTRUCTION | 2.31 | 0 | 0 | 0
17 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at 3rd site for SALKUMARHAT PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000066/2022-2023 | 338/ALD | 02/05/2022 | 01/10/2024 | SUBRATA DAS | 24.16 | 22.94 | 94.96 | 8
18 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Salkumarhat Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000728/2023-2024 | 2299/NMD-II | 31/07/2023 | 30/08/2023 | MADHAB SAHA | 20.89 | 0 | 0 | 100
Total | [13 empty] | 332.96 | 37.3 | 11.2