## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JASHODANGA WATER SUPPLY SCHEME | SM/10668 | Augmentation | Providing balance FHTC for Jashodanga PWSSunder Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000218/2023-2024 | 1559/ALD | 23/08/2023 | 22/09/2023 | JUGAL CHOUDHURY | 1.67 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JASHODANGA WATER SUPPLY SCHEME | SM/10668 | Augmentation | Providing FHTC in school in Josodanga PWSS under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000498/2022-2023 | 3362/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.36 | 0.36 | 100 | 100
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JASHODANGA WATER SUPPLY SCHEME | SM/10668 | Augmentation | Laying of new UPVC/DI pipeline for replacement of 75mm dia UPVC pipe with 90mm dia pipeline, gap filling and re distribution system along with the others allied works under Jashodanga PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - II Block | ORD/000005/2023-2024 | 26/ALD | 06/04/2023 | 27/09/2024 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 44.98 | 20.52 | 45.63 | 45
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JASHODANGA WATER SUPPLY SCHEME | SM/10668 | Augmentation | Reparing of Pump House at HW site and 2nd TW site of Jashodanga PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000568/2024-2025 | 5384/ALD | 17/03/2025 | 16/05/2025 | TAPASH KUMAR BHOWMICK | 0.96 | 0 | 0 | 0
Total | [13 empty] | 47.97 | 20.89 | 43.54