## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | Construction of pump House, boundary wall, laying of UPVC pipe linr & Rising main connection for Purba Chepani PWSS proposed 4th TW SITE under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000519/2022-2023 | 3494/ALD | 23/03/2023 | 21/06/2023 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 41.66 | 0 | 0 | 48
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | Providing balance FHTC for Purba Chepani PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000247/2023-2024 | 1589/ALD | 25/08/2023 | 24/09/2023 | ANIRBAN KAR | 3.32 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | New Laying of UPVC/DI pipeline, Providing FHTC and other allied works for Augmentation of Purba Chepani PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000193/2022-2023 | 1220/ALD | 10/08/2022 | 09/10/2022 | SREE MAA CONSTRUCTION | 21.55 | 7 | 32.47 | 94
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | Retrofitting of pipeline etc. for "Jal Swapno Program" (FHTC for every house hold) under Purba Chenpani PWSS under Alipurduar-II Block under Alipurduar Division, PHE Dte.(Re-tenter) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000079/2022-2023 | 443/ALD | 13/05/2022 | 12/06/2022 | MATRI ENTERPRISE | 4.2 | 4.06 | 96.71 | 10
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 3607/ALD | 24/10/2024 |  | Resource Division | 5.11 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 |  | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 |  | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
Total | [13 empty] | 203.86 | 11.06 | 5.43