## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. | SM/10670 | Augmentation | Construction of pumphouse, boundary wall,laying of UPVC pipeline & rising main connection for Salsalabari PWSS proposed 4th TW site PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000515/2022-2023 | 3400/ALD | 16/03/2023 | 14/06/2023 | BRAJA GOPAL SAHA | 39.58 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. | SM/10670 | Augmentation | Laying of new UPVC / DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, Land Development works, Construction of surface drain, supply of CIDF specials and other allied works in connection with the Salsalabari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000359/2023-2024 | 2745/ALD | 14/12/2023 | 06/02/2025 | MATRI ENTERPRISE | 16.16 | 0 | 0 | 100
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. | SM/10670 | Augmentation | Providing FHTC in school in Salsalabari PWSS under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - II Block | ORD/000497/2022-2023 | 3361/ALD | 14/03/2023 | 13/04/2023 | HARIDAS GHOSH | 0.29 | 0.29 | 100 | 100
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. | SM/10670 | Augmentation | Sinking of 250 mm x 200 mm x 150 mtr Big dia TW by reverse rotary drilling method at 4th TW site of Salsalabari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000029/2025-2026 | 438/ALD | 30/04/2025 | 30/05/2025 | MADHAB SAHA | 11.51 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. | SM/10670 | Augmentation | Reparing of Pump House at HW and 2nd TW site of SALSALABARI PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000567/2024-2025 | 5383/ALD | 17/03/2025 | 16/05/2025 | HARI CONSTRUCTION | 0.96 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. | SM/10670 | Augmentation | Restoration of damaged FHTCs and replacement of Old damaged pipelines at Salsalabari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000079/2025-2026 | 977/ALD | 12/06/2025 | 26/07/2026 | KOUSHIK BHOWMICK | 3.88 | 0 | 0 | 0
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. | SM/10670 | Augmentation | New Laying of UPVC/DI Pipe line, dismantling concrete road and recasting same and other allied works at Salsalabari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - II Block | ORD/000284/2022-2023 | 1638/ALD | 19/09/2022 | 02/04/2026 | NARENDRA BHADANI. | 30.82 | 29.6 | 96.03 | 98
Total | [13 empty] | 103.21 | 29.89 | 28.96