## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME | SM/10672 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Paschim Khairbari water supply scheme, TW no IV under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000855/2023-2024 | 2438/NMD-II | 11/08/2023 | 10/09/2023 | M/S MATRI CONSTRUCTION | 10.95 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME | SM/10672 | Augmentation | Construction of pump house, boundary wall and Rising main for 4th Tube well site at Paschim Khairbari PWSS of Birpara Sub-Division under Alipurduar Division, PHE Dte. (SM/10672) | Alipurduar RWS | RWS Madarihat - Birpara Block | ORD/000501/2023-2024 | 819/ALD | 14/03/2024 | 02/10/2025 | TAPASH KUMAR BHOWMICK | 16.68 | 0 | 0 | 70
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME | SM/10672 | Augmentation | Continuation of work of Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte.(from 01.01.2025 to 31.03.2025) | Alipurduar RWS | JUNIOR ENGINEER | ORD/000460/2024-2025 | 4555/ALD | 30/12/2024 | 30/03/2025 | SASANKA ROY | 1.2 | 0 | 0 | 0
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME | SM/10672 | Augmentation | Continuation of work of Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte.(from 01.01.2025 to 31.03.2025) | Birpara A.E | Alipurduar Sub Division,Birpara Sub Division,RWS Falakata Block | ORD/000461/2024-2025 | 4556/ALD | 30/12/2024 | 30/03/2025 | BHAGWATI BHUJEL | 1.2 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME | SM/10672 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME | SM/10672 | Augmentation | Laying of new HDPE/DI pipeline and replacement of Old distribution line and repairing of FHTC for Augmentation of paschim Khairbari PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Madarihat - Birpara Block | ORD/000591/2024-2025 | 5504/ALD | 21/03/2025 | 20/05/2025 | MONORAMA ENTERPRISE | 13.99 | 0 | 0 | 0
Total | [13 empty] | 118.37 | 0 | 0