## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME | SM/10672 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Paschim Khairbari water supply scheme, TW no IV under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000855/2023-2024 | 2438/NMD-II | 11/08/2023 | 10/09/2023 | M/S MATRI CONSTRUCTION | 10.95 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME | SM/10672 | Augmentation | Construction of pump house, boundary wall and Rising main for 4th Tube well site at Paschim Khairbari PWSS of Birpara Sub-Division under Alipurduar Division, PHE Dte. (SM/10672) | Alipurduar RWS | RWS Madarihat - Birpara Block | ORD/000501/2023-2024 | 819/ALD | 14/03/2024 | 12/07/2024 | TAPASH KUMAR BHOWMICK | 16.68 | 0 | 0 | 70
Total | [13 empty] | 27.63 | 0 | 0