## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME | SM/10673 | Augmentation | Retrofitting of pipeline with DI/UPVC pipeline for JAL SWAPNO programme (FHTC for every household) for LOKNATHPUR WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000499/2021-2022 | 3004/ALD | 15/03/2022 | 14/05/2022 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 20.09 | 16.34 | 81.31 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME | SM/10673 | Augmentation | Construction of pathway with paver block & land development of Loknathpur HW site WSS (Western part of GADA rivert) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000082/2022-2023 | 446/ALD | 13/05/2022 | 12/06/2022 | MATARA CONSTRUCTION CO | 4.21 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME | SM/10673 | Augmentation | Construction of pathway with paver block & land development of Loknathpur HW site & 2nd site WSS (Western part of GADA rivet) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000083/2022-2023 | 447/ALD | 13/05/2022 | 12/06/2022 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.19 | 0 | 0 | 0
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME | SM/10673 | Augmentation | Providing FHTC in school in Loknathpur PWSS under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - II Block | ORD/000494/2022-2023 | 3358/ALD | 14/03/2023 | 13/04/2023 | HARIDAS GHOSH | 0.22 | 0 | 0 | 100
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME | SM/10673 | Augmentation | Providing FHTC in school in Loknathpur PWSS under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - II Block | ORD/000505/2022-2023 | .3358/ALD | 14/03/2023 | 13/04/2023 | HARIDAS GHOSH | 0.22 | 0 | 0 | 100
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME | SM/10673 | Augmentation | Laying of rising main line HDPE PN10, horizontal boring by HDD method, bridge and culvert crossing, construction of pathway, surface drain and chatal, installation of paver block along with the others allied works at Loknathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000393/2023-2024 | 204/ALD | 16/01/2024 | 10/04/2025 | SOUVIK ROY PALADHI | 26.65 | 12.58 | 47.2 | 60
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME | SM/10673 | Augmentation | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing, construction of RCC pillars for supporting DI Pipe, surface drain and others allied works in connection with the Augmentation of Loknathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000408/2024-2025 | 4535/ALD | 26/12/2024 | 24/02/2025 | SOUVIK ROY PALADHI | 80.87 | 0 | 0 | 0
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME | SM/10673 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
Total | [13 empty] | 210.8 | 28.92 | 13.72