## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME | SM/10674 | Augmentation | Cons. Of balance portion of pump house, boundary wall, rising main, laying of DI and UPVC pipeline for Aug. of Banchukamari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000220/2023-2024 | 1580/ALD | 24/08/2023 | 22/12/2023 | HITANGSHU CHOUDHURY | 20.36 | 8.25 | 40.52 | 35
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME | SM/10674 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 1705/ALD | 21/09/2022 | 21/09/2022 | Resource Division | 61.6 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME | SM/10674 | Augmentation | Construction of Piller and Repairing of pipeline with GI Pipe near the house of Durga Oraon, kamal Roy & Banchukamari 1No. BFP School for Banchukamari WSS unedr Alipurduar Division, PHE Dte | Alipurduar RWS | RWS Madarihat - Birpara Block | ORD/000232/2022-2023 | 1229/ALD | 10/08/2022 | 09/09/2022 | TAPASH DAS | 3.07 | 0 | 0 | 80
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME | SM/10674 | Augmentation | Laying of UPVC and DI distribution line, repairing and renovation of 2nos pump house for Aug. Of Banchukamari PWSS Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division | Birpara Sub Division,JUNIOR ENGINEER | ORD/000477/2023-2024 | 695/ALD | 07/03/2024 | 03/09/2024 | DAS CONSTRUCTION | 50.59 | 35.81 | 70.78 | 2
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME | SM/10674 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME | SM/10674 | Augmentation | Gap filling of distribution pipeline and other allied works for Satkodali and adjoining area under Banchukamari PWSS within Alipurduar-I Block under Alipurduar Division, PHE Dte. | HQ-A.E | JUNIOR ENGINEER | ORD/000207/2025-2026 | 2351/ALD | 10/11/2025 | 24/01/2026 | DAS CONSTRUCTION | 68.41 | 0 | 0 | 0
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME | SM/10674 | Augmentation | Repairing of Old OHR at Banchukamari PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | JUNIOR ENGINEER | ORD/000241/2025-2026 | 3200/ALD | 12/03/2026 | 10/06/2026 | DAS CONSTRUCTION | 11.32 | 0 | 0 | 0
Total | [13 empty] | 279.36 | 44.06 | 15.77