## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF MUNSHIPARA WATER SUPPLY SCHEME | SM/10675 | Augmentation | Laying of new UPVC/DI pipeline for replacement of 75mm dia UPVC pipe with 90mm dia pipeline, gap filling and re distribution of branch line in the distribution system along with the others allied works under Munshipara PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000516/2022-2023 | 3401/ALD | 16/03/2023 | 26/10/2025 | NARENDRA BHADANI. | 90.61 | 0 | 0 | 85
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF MUNSHIPARA WATER SUPPLY SCHEME | SM/10675 | Augmentation | Reparing of Pump House at HEADWORK site of MUNSHIPARA PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000579/2024-2025 | 5393/ALD | 17/03/2025 | 16/05/2025 | TAPASH DAS | 0.94 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF MUNSHIPARA WATER SUPPLY SCHEME | SM/10675 | Augmentation | Reparing of Pump House at 2nd TW site of MUNSHIPARA PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000581/2024-2025 | 5395/ALD | 17/03/2025 | 16/05/2025 | TAPASH DAS | 0.79 | 0 | 0 | 0
Total | [13 empty] | 92.35 | 0 | 0