## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME | SM/10676 | Augmentation | Laying of DI pipe of Different Dia and other works For TAPSHIKHATA PWSS at Alipurduar -I Block under Alipurduar Division , PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000070/2022-2023 | 435/ALD | 13/05/2022 | 12/06/2022 | KAMALESH ROY | 4.76 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME | SM/10676 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Tapshikhata WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000349/2021-2022 | 2142/ALD | 06/01/2022 | 05/02/2022 | DEBAJYOTI SUTRADHAR | 5.02 | 5.02 | 99.99 | 52
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME | SM/10676 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 3608/ALD | 24/10/2024 | 24/10/2024 | Resource Division | 4.11 | 0 | 0 | 0
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME | SM/10676 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME | SM/10676 | Augmentation | Laying of distribution line with HDPE,UPVC and CI/DI pipes, laying of paver block at pump house no-1 and 2 and providing FHTC for Aug. Of Tapshikhata PWSS under Alipurduar Division. | Alipurduar RWS,Alipurduar Sadar Sub Division,HQ-A.E | Birpara Sub Division,JUNIOR ENGINEER | ORD/000469/2023-2024 | 675/ALD | 06/03/2024 | 24/02/2026 | TAPASH DAS | 43.25 | 26.98 | 62.38 | 10
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME | SM/10676 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
Total | [13 empty] | 195.5 | 32 | 16.37