## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/10677 | Augmentation | New Laying of UPVC/DI pipeline,and other allied works including filling of gap in the distribution system for Augmentation of Chandirjhar PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000231/2022-2023 | 1228/ALD | 10/08/2022 | 09/09/2022 | MATRI ENTERPRISE | 3.21 | 2.87 | 89.42 | 8
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/10677 | Augmentation | Retrofitting of pipeline for the 'Jal Sapno' programme and providing FHTC Connection under Chandirjhar WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000164/2021-2022 | 1305/ALD | 05/10/2021 | 04/12/2021 | SASANKA ROY | 50.06 | 0 | 0 | 36
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/10677 | Augmentation | Laying Distribution pipe line by DI pipe(with piller ) along the flack of Alipurduar - Bhatibari - Salsalabari Road of Chandijhar WSS under Alipurduar Division , PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000075/2022-2023 | 440/ALD | 13/05/2022 | 12/06/2022 | SREE MAA CONSTRUCTION | 4.59 | 4.52 | 98.58 | 9
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/10677 | Augmentation | Land development of 3rd Tubewell site at Chandirjhar WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000236/2022-2023 | 1232/ALD | 10/08/2022 | 09/09/2022 | DULAL DAS | 1.36 | 1.26 | 92.09 | 9
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/10677 | Augmentation | Supply of CIDF Specials & Jeffy Coupling for Augmentation of Chandirjhar (SM/10677) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000402/2024-2025 | 4538/ALD | 26/12/2024 | 25/01/2025 | MAHENDRA CHHETRI | 19.05 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/10677 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/10677 | Augmentation | Repairing of pump house at headwork site of Chandirjhar PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000175/2025-2026 | 1857/ALD | 26/08/2025 | 25/10/2025 | HARI CONSTRUCTION | 1.01 | 0 | 0 | 0
Total | [13 empty] | 153.65 | 8.65 | 5.63