## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/10677 | Augmentation | Laying of new UPVC/DI pipeline for filling of Gap in the distribution system and other allied works in connection with the complain address in the CMRO portal in the command area of Chandirjhar PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - II Block | ORD/000391/2023-2024 | 202/ALD | 16/01/2024 | 12/09/2024 | KAMALESH ROY | 14.05 | 0 | 0 | 65
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/10677 | Augmentation | Supply of CIDF Specials & Jeffy Coupling for Augmentation of Chandirjhar (SM/10677) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000402/2024-2025 | 4538/ALD | 26/12/2024 | 25/01/2025 | MAHENDRA CHHETRI | 19.05 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/10677 | Augmentation | Retrofitting of pipeline for the 'Jal Sapno' programme and providing FHTC Connection under Chandirjhar WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000164/2021-2022 | 1305/ALD | 05/10/2021 | 04/12/2021 | SASANKA ROY | 50.06 | 0 | 0 | 36
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/10677 | Augmentation | Laying Distribution pipe line by DI pipe(with piller ) along the flack of Alipurduar - Bhatibari - Salsalabari Road of Chandijhar WSS under Alipurduar Division , PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000075/2022-2023 | 440/ALD | 13/05/2022 | 12/06/2022 | SREE MAA CONSTRUCTION | 4.59 | 4.52 | 98.58 | 9
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/10677 | Augmentation | New Laying of UPVC/DI pipeline,and other allied works including filling of gap in the distribution system for Augmentation of Chandirjhar PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000231/2022-2023 | 1228/ALD | 10/08/2022 | 09/09/2022 | MATRI ENTERPRISE | 3.21 | 2.87 | 89.42 | 8
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/10677 | Augmentation | Land development of 3rd Tubewell site at Chandirjhar WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000236/2022-2023 | 1232/ALD | 10/08/2022 | 09/09/2022 | DULAL DAS | 1.36 | 1.26 | 92.09 | 9
Total | [13 empty] | 92.33 | 8.65 | 9.37