## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME | SM/11401 | Augmentation | Providing House connection and extension of pipe line for Silbarihat area within PATLAKHAWA PWSS under Alipurduar Division PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000072/2021-2022 | 879/ALD | 03/09/2021 | 02/11/2021 | TAPASH KUMAR BHOWMICK | 45.7 | 12.33 | 26.97 | 76.33
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME | SM/11401 | Augmentation | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Silbarihat under Patlakhawa PWSS. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000468/2021-2022 | 2766/ALD | 25/02/2022 | 26/04/2022 | TAPASH KUMAR BHOWMICK | 42.34 | 30.19 | 71.31 | 74.67
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME | SM/11401 | Augmentation | Laying of Different Dia pipeline And providing FHTC For Patlakhowa and Adjoining area under Patlakhowa PWSS at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000122/2022-2023 | 919/ALD | 07/07/2022 | 21/08/2022 | M/S DUTTA AND CO | 72.26 | 40.46 | 55.99 | 70
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME | SM/11401 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of Patlakhawa Piped Water Supply Scheme | Alipurduar RWS | Birpara Sub Division | ORD/000239/2022-2023 | 1331/ALD | 24/08/2022 | 23/10/2022 | UTTAM SAHA | 29.37 | 28.52 | 97.1 | 97
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME | SM/11401 | Augmentation | Extension and Replacement of damaged pipeline under Patlakhawa PWSS under Alipurduar Division, P.H.E. Dte.(Part-C) | Alipurduar RWS | Birpara Sub Division | ORD/000183/2020-2021 | 1008/ALD | 12/11/2020 | 11/01/2021 | JAI BHARAT COMMERCIAL CORPORATION | 14.4 | 0.25 | 1.74 | 100
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME | SM/11401 | Augmentation | Extension and Replacement of damaged pipeline under Patlakhawa PWSS under Alipurduar Division, P.H.E. Dte.(Part-C) | Alipurduar RWS | Birpara Sub Division | ORD/000184/2020-2021 | 1009/ALD | 12/11/2020 | 11/01/2021 | M/S PALIT ENTERPRISE | 14.4 | 0.28 | 1.92 | 70
7 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME | SM/11401 | Augmentation | Supply & delivery,of Electro mechanical components at Patlakhawa Water Supply Scheme,TW-I in the dist of ALIPURDUAR under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000868/2021-2022 | 632/AMSD | 03/03/2022 | 18/03/2022 | MADHAB SAHA | 2.35 | 2.35 | 100 | 68
8 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME | SM/11401 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with cu wound line voltage corrector for Augmentation of PATLAKHAWA Water Supply Scheme,TW no .I under NMD-II, PHE Dte. Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000034/2023-2024 | 968/NMD-II | 13/05/2023 | 12/06/2023 | SUMON ELECTRICAL | 11.02 | 10.34 | 93.83 | 100
9 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME | SM/11401 | Augmentation | Quotation for new service connection at Patlakhawa P/H No- III, Application NO- 4003028004 |  |  | BILL/00007/2022-2023 | BP-97/22-23 | 02/12/2022 |  | WBSEDCL | 1.34 | 0 | 0 | 0
10 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME | SM/11401 | Augmentation | Quotation for new service connection at PATLAKHAWA w/s scheme T/W no. III, Application no. 4003028004 |  |  | VCH/001530/2022-2023 | null | 30/11/2022 |  | WBSEDCL | 1.34 | 0 | 0 | 0
Total | [13 empty] | 234.52 | 124.72 | 53.18