## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Schedule for: Supply, delivery and installation of 30 KVA servo motor operated Copper wound line voltage corrector at Purba Kathalbari Water Supply Scheme TW No.-II under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000651/2021-2022 | 1097/NMD-II | 20/09/2021 | 20/10/2021 | NIRMAN | 3.94 | 3.94 | 100 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site for Purba Kathalbari Zone-III PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000168/2022-2023 | 1008/ALD | 15/07/2022 | 13/10/2022 | MADHAB SAHA | 45.9 | 39.6 | 86.27 | 86
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Construction of OHR 200cum for PURBA KATHALBARI ZONE-II Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000161/2022-2023 | 991/ALD | 15/07/2022 | 11/01/2023 | MS DEYS CONSTRUCTION | 55.5 | 25 | 45.05 | 55
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying of different dia. Pipeline and providing FHTC for Southern side of Purba Kathalbari Zone (II) PWSS and surrounding areas at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000167/2022-2023 | 997/ALD | 15/07/2022 | 13/09/2022 | M/S JHA CONSTRUCTION | 99.69 | 76.99 | 77.23 | 27
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying of different dia. Pipeline and providing FHTC for Purba Kathalbari Zone(IV) PWSS area and surrounding, Alipurduar-I Block under Alipurduar Division, PHE Dte.(Part-A) | Alipurduar RWS | Birpara Sub Division | ORD/000165/2022-2023 | 995/ALD | 15/07/2022 | 13/09/2022 | DAS ENTERPRISE | 99.06 | 67.23 | 67.87 | 27
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Purba Kathalbari PWSS under Alipurduar Division, PHE Dte. Part-3 | Alipurduar RWS | Birpara Sub Division | ORD/000144/2022-2023 | 981/ALD | 15/07/2022 | 29/08/2022 | MAHENDRA CHHETRI | 24.2 | 7.33 | 30.29 | 26
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for PurbaKathalbari PWSS under Alipurduar Division, PHE Dte. Part-4 | Alipurduar RWS | Birpara Sub Division | ORD/000145/2022-2023 | 982/ALD | 15/07/2022 | 29/08/2022 | DAS CONSTRUCTION | 24.14 | 0 | 0 | 27
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying Distribution of pipeline with DI and UPVC pipeline along with FHTC Connection at Jogendranagar area, Purba Kathalbari WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000159/2022-2023 | 989/ALD | 15/07/2022 | 13/09/2022 | UTTAM KUMAR DUTTA | 98.45 | 87.43 | 88.8 | 27
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying of different dia. Pipeline and providing FHTC for Purba Kathalbari Zone(IV) PWSS area and surrounding area of NH-31D at Alipurduar-I Block under Alipurduar Division, PHE Dte.(Part-B) | Alipurduar RWS | Birpara Sub Division | ORD/000166/2022-2023 | 996/ALD | 15/07/2022 | 13/09/2022 | NARAYAN CHANDRA SAHA | 99.18 | 75.08 | 75.7 | 76
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Development of TW, Yield testing with BHT Pump and water sample collection and chemical test at different tubewell of Purba Kathal Bari PWSS at Alipurduar-I Block, Alipurduar Division PHED. | Alipurduar RWS |  | ORD/000351/2022-2023 | 2495/ALD | 13/12/2022 | 11/02/2023 | SAMIRON PODDER | 5.68 | 0 | 0 | 0
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Providing FHTC from existing distribution system as per specification for PURBA KATHALBARI PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000288/2023-2024 | 1996/ALD | 15/09/2023 | 14/11/2023 | M/S SIBU DEY AND CO | 24.2 | 0 | 0 | 0
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site along with repairing of 1 no. pump house for Purba Kathalbari Zone-I PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000169/2022-2023 | 1007/ALD | 15/07/2022 | 13/10/2022 | SAMIRON PODDER | 43.06 | 40.49 | 94.02 | 0
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Soil investigation work at 4 different places of Purba Kanthalbari within Alipurduar District under Alipurduar Division PHE Dte. | Alipurduar RWS |  | ORD/000157/2022-2023 | 1006/ALD | 15/07/2022 | 14/08/2022 | MABCO CONSULTANT, | 4.87 | 4.87 | 100 | 27
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2022-2023 | 1590/ALD | 14/09/2022 | 14/09/2022 | Resource Division | 130.15 | 0 | 0 | 0
15 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR PURBA KATHALBARI zONE-III P/H NO.I |  |  | BILL/00677/2023-2024 | BP-2023-24-197 | 22/06/2023 | 22/06/2023 | WBSEDCL | 1.71 | 0 | 0 | 0
16 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT PURBA KATHALBARI PWSS PALASHBARI, FLOOD SHELTER, ZONE-I,P/H NO-I |  |  | BILL/01448/2023-2024 | BP-2023-24-293 | 21/08/2023 | 21/08/2023 | WBSEDCL | 6.38 | 0 | 0 | 0
17 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR PURBA KATHALBARI zONE-III P/H NO.II |  |  | BILL/00678/2023-2024 | BP-2023-24-196 | 22/06/2023 | 22/06/2023 | WBSEDCL | 1.71 | 0 | 0 | 0
18 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR PURBA KATHALBARI zONE-IV P/H NO.I |  |  | BILL/00676/2023-2024 | BP-2023-24-198 | 22/06/2023 | 22/06/2023 | WBSEDCL | 1.71 | 0 | 0 | 0
19 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR PURBA KATHALBARI zONE-I P/H NO.II |  |  | BILL/00679/2023-2024 | BP-2023-24-195 | 22/06/2023 | 22/06/2023 | WBSEDCL | 1.71 | 0 | 0 | 0
20 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying Distribution of pipeline with DI and UPVC pipeline along with FHTC Connection for Purba Kathalbari area, Purba Kathalbari WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000158/2022-2023 | 988/ALD | 15/07/2022 | 13/09/2022 | NEOGI ENTERPRISE | 98.79 | 80.1 | 81.08 | 30
21 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Construction of 150cum. OHR for PURBA KATHALBARI ZONE-IV Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000149/2022-2023 | 984/ALD | 15/07/2022 | 04/07/2024 | MAHENDRA CHHETRI | 50.44 | 38.98 | 77.29 | 52
22 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying of different dia. Pipeline and providing FHTC for Northern side of Purba Kathalbari Zone (II) PWSS and surrounding areas at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000141/2022-2023 | 978/ALD | 15/07/2022 | 13/09/2022 | DILIP MAHATO | 99.77 | 76.96 | 77.14 | 15
23 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection surrounding Sirubari area, Purba Kathalbari WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division,RWS Madarihat - Birpara Block | ORD/000163/2022-2023 | 993/ALD | 15/07/2022 | 05/09/2024 | MS DEYS CONSTRUCTION | 99.93 | 69.73 | 69.78 | 85
24 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection surrounding Palashbari area, Purba Kathalbari WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000164/2022-2023 | 994/ALD | 15/07/2022 | 11/01/2023 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 87.56 | 53.26 | 60.83 | 28
25 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | Alipurduar RWS | JUNIOR ENGINEER | ORD/000416/2022-2023 | 2731/ALD | 30/12/2022 | 30/12/2023 | KAMALESH ROY | 4.8 | 4.58 | 95.42 | 100
26 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Deputy Superintending Engineer, North Bengal Circle-I , P.H.E. Dte.(from 01.03.2023 to 29.02.2024) | HQ-A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000473/2022-2023 | 3232/ALD | 27/02/2023 | 27/02/2024 | MAHENDRA CHHETRI | 4.8 | 0 | 0 | 0
27 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Purba Kanthalbari water supply scheme, TW no I and II of Zone-IV under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000050/2023-2024 | 1107/NMD-II | 05/06/2023 | 05/07/2023 | SUMON ELECTRICAL | 22.86 | 20.21 | 88.4 | 70
28 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Construction of 250cum OHR for PURBA KATHALBARI ZONE-I Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar RWS | ORD/000155/2022-2023 | 987/ALD | 15/07/2022 | 11/01/2023 | NEOGI ENTERPRISE | 57.61 | 38.03 | 66.01 | 35
29 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Construction of OHR 200cum for PURBA KATHALBARI ZONE-III Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000152/2022-2023 | 986/ALD | 15/07/2022 | 11/01/2023 | MADHAB SAHA | 55.36 | 45.63 | 82.43 | 51
30 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Purba Kanthalbari water supply scheme, TW no I and II of Zone-III under Northern Mechanical Division-II, PHE Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000048/2023-2024 | 1085/NMD-II | 01/06/2023 | 01/07/2023 | M/S P.P ELECTRICALS | 22.85 | 22.54 | 98.64 | 100
31 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 3612/ALD | 24/10/2024 | 24/10/2024 | Resource Division | 7.78 | 0 | 0 | 0
32 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR PURBA KATHALBARI PWSS ZONE-II P/H NO-II |  |  | BILL/02806/2023-2024 | BP-2023-24-646 | 29/02/2024 | 29/02/2024 | WBSEDCL | 9.8 | 0 | 0 | 0
33 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | QUOTATION CHARGES FOR PURBAKATHALBARI PWSS, ZONE-II PH NO-II |  |  | BILL/00276/2024-2025 | BP-80/24-25 | 16/05/2024 | 16/05/2024 | WBSEDCL | 11.03 | 0 | 0 | 0
34 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | New Service Connection charges for Purba Kathalbari Zone-IV PH NO-II under NMD-II |  |  | BILL/01888/2024-2025 | BP-444/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 6.36 | 0 | 0 | 0
35 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
36 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site for Purba Kathalbari Zone-IV PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000143/2022-2023 | 980/ALD | 15/07/2022 | 04/07/2024 | MAHENDRA CHHETRI | 46.09 | 27.06 | 58.71 | 60
37 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Purba Kanthalbari water supply scheme, TW no I and II of Zone-II under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000794/2023-2024 | 2366/NMD-II | 08/08/2023 | 03/04/2025 | SUMON ELECTRICAL | 22.5 | 0 | 0 | 80
38 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte.(from 01.01.2024 to 31.12.2024) | Alipurduar RWS | JUNIOR ENGINEER | ORD/000499/2023-2024 | 488/ALD | 15/02/2024 | 15/02/2025 | SASANKA ROY | 4.8 | 3.54 | 73.82 | 0
39 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying of DI and HDPE pipeline, Trenchless Pipe laying by HDD Process & other works for PURBA KATHALBARI ZONE-I 3rd pump house area for Purba Kathalbari PWSS of Alipurduar RWS Sub-Division under Alipurduar Division, PHE Dte. (SM/11459) | Alipurduar RWS | Birpara Sub Division,RWS Madarihat - Birpara Block | ORD/000503/2023-2024 | 821/ALD | 14/03/2024 | 07/07/2025 | KAJAL KUMAR DE | 39.26 | 0 | 0 | 70
40 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying of different dia., CIDF, DI, UPVC, HDPE Pipeline, Trenchless Pipe laying by HDD Process, HDPE pipe line for left out household connection,Trial and run the entire PURBA KATHALBARI ZONE-3 PWSS Scheme with maintaining for 3 months after successfully running water, cons. of surface drain, pathway at H/W site and other works works for Purba Kathalbari PWSS of Alipurduar RWS Sub-Division under Alipurduar Division, PHE Dte. (SM/11459) | Alipurduar RWS | Birpara Sub Division,RWS Madarihat - Birpara Block | ORD/000534/2023-2024 | 892/ALD | 15/03/2024 | 05/03/2025 | MADHAB SAHA | 49.29 | 4.78 | 9.69 | 60
41 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
42 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Replacement of damaged pipeline with HDPE pipes for Purba Kathalbari Zone-I PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000105/2025-2026 | 1223/ALD | 01/07/2025 | 30/08/2025 | DILIP MAHATO (OPC) PRIVATE LIMITED | 5.3 | 0 | 0 | 0
43 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying of pipeline distribution system (Parallel and left out Area) and other allied works at Purba Kathalbari Zone-I PWSS within APD-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Madarihat - Birpara Block | ORD/000211/2025-2026 | 2414/ALD | 18/11/2025 | 17/01/2026 | ANIRBAN DEY SARKAR CONSTRUCTION | 54.38 | 0 | 0 | 0
44 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying of pipeline distribution system (Parallel and left out Area) and other allied works at Purba Kathalbari Zone-II PWSS within APD-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000158/2025-2026 | 1743/ALD | 13/08/2025 | 12/10/2025 | ANIRBAN DEY SARKAR CONSTRUCTION | 41.04 | 0 | 0 | 0
45 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site for Purba Kathalbari Zone-II PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000142/2022-2023 | 979/ALD | 15/07/2022 | 30/06/2025 | JYOTI CHHETRI | 45.88 | 38.27 | 83.42 | 61
46 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Purba Kanthalbari water supply scheme, TW no I and II of Zone-I under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000801/2022-2023 | 368/NMD-II | 22/02/2023 | 02/12/2024 | ALPHA ENTERPRISE | 22.84 | 19.58 | 85.74 | 100
Total | [13 empty] | 1880.71 | 971.21 | 51.64