## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Providing House Connection (FHTC) at Kumargram WSS under Alipurduar Division, PHE Dte. Part-4 | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000148/2022-2023 | 1002/ALD | 15/07/2022 | 14/08/2022 | DILIP MAHATO | 5.04 | 0 | 0 | 43
2 | ALIPURDUAR | Kumargram | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Providing House Connection (FHTC) at Kumargram WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000150/2022-2023 | 1003/ALD | 15/07/2022 | 14/08/2022 | DILIP MAHATO | 5.04 | 0 | 0 | 42
3 | ALIPURDUAR | Kumargram | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Construction of 150cum. OHR for KUMARGRAM ZONE-IV Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000147/2022-2023 | 983/ALD | 15/07/2022 | 11/01/2023 | MATRI ENTERPRISE | 50.41 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Soil investigation work at 4 different places of Kumargram within Alipurduar District under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000156/2022-2023 | 1005/ALD | 15/07/2022 | 14/08/2022 | MOYTEC | 4.88 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Providing FHTC at Kumargram WSS under Alipurduar Division, PHE Dte. Part-3 | Alipurduar Sadar Sub Division |  | ORD/000146/2022-2023 | 1001/ALD | 15/07/2022 | 14/08/2022 | DILIP MAHATO | 5.04 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Land development, construction of pathway of HWS and culvert crossing with DI pipe under Kumargram TG WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000350/2022-2023 | 2492/ALD | 13/12/2022 | 13/03/2023 | HARIDAS GHOSH | 12.45 | 0 | 0 | 43
7 | ALIPURDUAR | Kumargram | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 206/ALD/2023-2024 | 02/05/2023 | 02/05/2023 | Resource Division | 5.44 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Quotation for new service connection at kumargram TG P/H No-II. Application No- 4003039118 |  |  | BILL/00019/2022-2023 | BP-107/22-23 | 19/12/2022 | 19/12/2022 | WBSEDCL | 1.58 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Quotation for new service connection at kumargram TG P/H No-I. Application No- 4003039105 |  |  | BILL/00018/2022-2023 | BP-108/22-23 | 19/12/2022 | 19/12/2022 | WBSEDCL | 1.58 | 0 | 0 | 0
10 | ALIPURDUAR | Kumargram | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Construction of 250cum. OHR for Kumargram TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000139/2022-2023 | 976/ALD | 15/07/2022 | 11/01/2023 | HARIDAS GHOSH | 57.62 | 0 | 0 | 100
11 | ALIPURDUAR | Kumargram | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for KUMARGRAM TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000210/2022-2023 | 1305/ALD | 22/08/2022 | 11/08/2024 | HARIDAS GHOSH | 81.11 | 0 | 0 | 90
12 | ALIPURDUAR | Kumargram | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC for KUMARGRAM TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000205/2022-2023 | 1304/ALD | 22/08/2022 | 20/12/2022 | GOUTAM KUMAR DAS | 94.63 | 0 | 0 | 80
13 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Hiring of Motor Cab (Non-air conditioned) for site visit of the Assistant Engineer , Alipurduar Mechanical Sub- Division, P.H.E. Dte. for Inspection of different PWSS under JJM like Newland TG , Kumargram TG & Sankosh TG under Northern Mechanical Division -II, P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000914/2023-2024 | 139/AMSD | 30/06/2023 | 31/08/2023 | MUSTAFI CONCERN | 0.69 | 0 | 0 | 100
14 | ALIPURDUAR | Kumargram | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Providing balance FHTC for KUMARGRAM TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000245/2023-2024 | 1791/ALD | 29/08/2023 | 23/08/2024 | HARI CONSTRUCTION | 13.16 | 0 | 0 | 81
15 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Kumargram TG water supply scheme, TW no II under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000003/2023-2024 | 770/NMD-II | 06/04/2023 | 06/05/2023 | BEE GEE CONSTRUCTION | 10.74 | 0 | 0 | 90
16 | ALIPURDUAR | Kumargram | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Supply of CIDF special for Kumargram TG Pwss Under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000239/2023-2024 | 1608/ALD | 25/08/2023 | 24/09/2023 | HARI CONSTRUCTION | 7.67 | 0 | 0 | 95
17 | ALIPURDUAR | Kumargram | Alipurduar Division | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Material Requisition To Resource Division |  |  | RTOR000106/2023-2024 | 130/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 9.2 | 0 | 0 | 0
18 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Kumargram TG water supply scheme, TW no I(H/W Site) under Northern Mechanical Division-II, PHE Dte.Alipurduar. |  |  | ORD/000017/2023-2024 | 902/NMD-II | 04/05/2023 | 03/06/2023 | MAA ENTERPRISES | 10.74 | 0 | 0 | 0
Total | [13 empty] | 377.02 | 0 | 0