## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | SUPPLY, INSTALLATION,COMMISSIONING AND TRIAL OPERATION OF ELECTRO MECHANICAL COMPONENTS OF RIGBORE T/W(2NOS.) FOR BANDAPANI AREA ALONG WITH CONS. OF 2NOS. P/H OF SIZE 3.00M X 3.60M |  |  | ORD/000335/2020-2021 | 1485/ALD | 27/01/2021 | 28/03/2021 | DILIP MAHATO | 22 | 3.75 | 17.06 | 25
2 | ALIPURDUAR | Madarihat | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | Construction of 150cum. OHR for Bandapani ZONE-II Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000137/2022-2023 | 974/ALD | 15/07/2022 | 06/01/2024 | MITHUN DAS | 49.89 | 43.12 | 86.43 | 86
3 | ALIPURDUAR | Madarihat | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | Supply Installation Commissioning and Trial Operation of Electro Mechanical components at Bandapani TG Hindi High School withing Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Part-2) | Birpara A.E |  | ORD/000234/2022-2023 | 1231/ALD | 10/08/2022 | 09/09/2022 | BHAGWATI BHUJEL | 3.8 | 3.3 | 86.91 | 24
4 | ALIPURDUAR | Madarihat | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | Soil investigation works at head works site for BANDAPANI TG AREA PWSS (ZONE-I) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000310/2022-2023 | 2134/ALD | 10/11/2022 | 10/12/2022 | MOYTEC | 0.7 | 0.64 | 91.89 | 0
5 | ALIPURDUAR | Madarihat | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | Tube well Boring by ODEX-165 method of drilling at Head work site, Construction of 1 no. Pump house and Boundary wall at headwork site, Rising Main and Distribution line with FHTC (Part-1) for BANDAPANI TG AREA PWSS (ZONE-I) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000285/2022-2023 | 1639/ALD | 19/09/2022 | 02/11/2024 | PRAMESH LAMA | 43.08 | 20.04 | 46.52 | 50
6 | ALIPURDUAR | Madarihat | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | Soil investigation works at head works site for BANDAPANI TG AREA PWSS (ZONE-2) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000312/2022-2023 | 2136/ALD/ | 10/11/2022 | 10/12/2022 | MOYTEC | 0.66 | 0.61 | 91.89 | 0
7 | ALIPURDUAR | Madarihat | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | Laying distribution system (Part-2) and providing FHTC for BANDAPANI TG AREA PWSS (ZONE-I) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000340/2022-2023 | 2249/ALD | 21/11/2022 | 31/03/2023 | PRAMESH LAMA | 52.84 | 30.31 | 57.37 | 83
8 | ALIPURDUAR | Madarihat | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | Construction of 150 cum OHR as per Departmental Design and drawing, Tube well Boring by ODEX-165 method of drilling 1 nos. respectively at H/W site, Rising main and distribution line (part-1) for BANDAPANI TG AREA PWSS (ZONE-II) under Birpara Sub-Division , Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000341/2022-2023 | 2250/ALD | 21/11/2022 | 14/05/2024 | SAMIRON PODDER | 88.7 | 85.63 | 96.53 | 85
9 | ALIPURDUAR | Madarihat | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | Construction of 1 no. Pump House, 1 no. Boundary wall at headwork site, distribution of pipeline and providing FHTC for BANDAPANI TG AREA PWSS (ZONE-II) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000296/2022-2023 | 1687/ALD | 20/09/2022 | 09/09/2024 | MITHUN DAS | 53.39 | 46.7 | 87.47 | 78
10 | ALIPURDUAR | Madarihat | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | Supply Installation Commissioning and Trial Operation of Electro Mechanical components at Bandapani TG Hindi High School within Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Part-1) | Birpara A.E | Alipurduar Sub Division | ORD/000233/2022-2023 | 1230/ALD | 10/08/2022 | 09/09/2022 | BHAGWATI BHUJEL | 3.92 | 3.88 | 99.1 | 25
11 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bandapani TG water supply scheme, TW no I and II of Zone-I and TW no I and II of Zone-II under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000020/2023-2024 | 936/NMD-II | 10/05/2023 | 09/06/2023 | ALPHA ENTERPRISE | 37.32 | 9.52 | 25.52 | 35
12 | ALIPURDUAR | Madarihat | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | Supply of drinking water through tanker by hired vehicle to mitigate drinking water crisis at Bandapani TG under Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000310/2023-2024 | 2175/ALD | 06/10/2023 | 20/11/2023 | NARENDRA BHADANI. | 3.48 | 3.48 | 100 | 100
13 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BANDAPANI TG TW NO-II |  |  | BILL/00065/2023-2024 | BP-2023-24-60 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.6 | 0 | 0 | 0
14 | ALIPURDUAR | Madarihat | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | New Connection for Assistant Engineer Alipurduar RWS Sub-Division PHE Reti Forest, Bandapani |  |  | BILL/00106/2022-2023 | 444/22-23/PFMS | 21/01/2023 | 21/01/2023 | WBSEDCL | 0.1 | 0 | 0 | 0
15 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BANDAPANI TG TW NO-I |  |  | BILL/00066/2023-2024 | BP-2023-24-59 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.6 | 0 | 0 | 0
16 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | QUOTATION FOR 3 PHASE UNIT METER ID -402728652 |  |  | BILL/01831/2023-2024 | BP-2023-24-330 | 27/09/2023 | 27/09/2023 | WBSEDCL | 0.1 | 0 | 0 | 0
17 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | Additional Quotation for BANDAPANI TG P/HNO-II(Application No-4003127203) |  |  | BILL/02163/2023-2024 | BP-2023-24-471 | 12/12/2023 | 12/12/2023 | WBSEDCL | 25.52 | 0 | 0 | 0
18 | ALIPURDUAR | Madarihat | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | Construction of pump house, boundary wall, TW boring (by ODEX-165 method of drilling) and Rising main for 2nd TW site at Bandapani PWSS (Zone-II) under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000367/2023-2024 | 83/ALD | 10/01/2024 | 06/09/2024 | MITHUN DAS | 24.21 | 19.15 | 79.11 | 85
19 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | New Service Connection Charges For BANDAPANI TG Zone-II PH NO-II Near RETI PWSS Under NMD-II in the dist. of ALIPURDUAR |  |  | BILL/00899/2025-2026 |  | 13/06/2025 | 13/06/2025 | WBSEDCL | 6.09 | 0 | 0 | 0
20 | ALIPURDUAR | Madarihat | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | Construction of Pump house (2nd TW site), Boundary wall (2nd site & OHR Site) and Gap filling of pipeline with DI/UPVC pipe, providing balance FHTC and rising main for (Zone-I and II) 2nd TW Site at Bandapani TG PWSS under Alipurduar Division, PHE Dte | Birpara A.E | Alipurduar Sub Division | ORD/000525/2026-2027 | 1909/ALD | 07/08/2026 | 05/12/2026 | JYOTI CHHETRI | 43.7 | 0 | 0 | 0
21 | ALIPURDUAR | Madarihat | Alipurduar Division | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 | New | Installation of Tubewell boring (by ODEX-165 method of drilling ) (Zone-II) at Bandapani PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000526/2026-2027 | 1910/ALD | 07/08/2026 | 21/09/2026 | RATAN DUTTA | 8.68 | 0 | 0 | 0
Total | [13 empty] | 471.38 | 270.15 | 57.31