## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Laying distribution system with new HDPE pipeline (Part-F) with Rising Main and delivery line connection, providing FHTC and other allied works for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000290/2022-2023 | 1644/ALD | 19/09/2022 | 18/11/2022 | TAPAN CHANDA | 49.13 | 35.12 | 71.48 | 44
2 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Laying distribution system with new DI line & Supply of necessary specials, construction of sluice valve chamber, Construction of pump house and boundary wall at HW site of Shrinathpur TG Area PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000336/2022-2023 | 2245/ALD | 21/11/2022 | 21/03/2023 | TRIBENI CONSTRUCTION | 14.48 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | 2 nos Tube well boring by ODEX-165 Method of drilling for the works implementation of Shrinathpur Tea Garden Area PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000354/2022-2023 | 2499/ALD | 13/12/2022 | 27/01/2023 | S.G. CONSTRUCTION | 13.14 | 10.24 | 77.94 | 0
4 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Laying distribution system with new HDPE pipeline (Part- E) and providing FHTC and others allied works for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000289/2022-2023 | 1643/ALD | 19/09/2022 | 18/11/2022 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 55.49 | 49.11 | 88.5 | 45
5 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Soil investigation works at head works site for SRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000311/2022-2023 | 2135/ALD | 10/11/2022 | 10/12/2022 | MOYTEC | 0.7 | 0.7 | 100 | 100
6 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Laying distribution system with new HDPE pipeline for providing FHTC in the Command area of Shrinathpur TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000193/2023-2024 | 1469/ALD | 16/08/2023 | 15/10/2023 | CHANDAN KIRTONIA | 13 | 13 | 100 | 100
7 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 1269/ALD | 11/08/2023 | 11/08/2023 | Resource Division | 21.78 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | New Service Connection Charge For Shrinathpur TG |  |  | BILL/00899/2023-2024 | BP-2023-24-224 | 13/07/2023 | 13/07/2023 | WBSEDCL | 0.81 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | New Service Connection Charge For Shrinathpur TG T/W NO.I |  |  | BILL/00900/2023-2024 | BP-2023-24-223 | 13/07/2023 | 13/07/2023 | WBSEDCL | 0.81 | 0 | 0 | 0
10 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Laying distribution system with new HDPE pipeline (Part- D) and providing FHTC and others allied works for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000288/2022-2023 | 1642/ALD | 19/09/2022 | 07/03/2025 | KAMALESH ROY | 45.33 | 31.15 | 68.72 | 100
11 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Construction of pathway, surface drain and chatal, land development, along with other allied works at Shrinathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000194/2023-2024 | 1470/ALD | 16/08/2023 | 09/10/2024 | KAMALESH ROY | 12.83 | 4.56 | 35.51 | 50
12 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Laying distribution system the new HDPE pipeline (Part-A) with rising and delivery line connection, providing FHTC and others allied works for Shrinathpur Tea Garden Area PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000392/2022-2023 | 2657/ALD/ | 22/12/2022 | 13/08/2024 | DEBAJYOTI SUTRADHAR | 96.35 | 94.46 | 98.03 | 95
13 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Laying distribution system with new HDPE pipeline (Part- G) with Rising Main and delivery line connection for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000291/2022-2023 | 1645/ALD | 19/09/2022 | 14/09/2023 | DEBAJYOTI SUTRADHAR | 62.99 | 61.3 | 97.32 | 45
14 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Laying distribution system with new DI line and Supply of necessary specials, construction of sluice valve chamber, Construction of pump house and boundary wall at 2nd site of Shrinathpur TG Area PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000337/2022-2023 | 2246/ALD | 21/11/2022 | 11/09/2024 | PRAPTI DUTTA | 11.32 | 11.07 | 97.76 | 100
15 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Laying distribution system with new HDPE pipeline (Part-H) with Rising Main and delivery line connection for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000292/2022-2023 | 1646/ALD | 19/09/2022 | 18/11/2022 | MADHAB SAHA | 56.38 | 54.16 | 96.07 | 45
16 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Construction of 300 cum OHR as per departmental design and drawing, soil investigation work, laying of DI/CI pipeline, supplying of CI Specials and other allied works at headwork site of Shrinathpur Tea Garden Area PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000412/2022-2023 | 2690/ALD | 23/12/2022 | 21/06/2023 | KAMALESH ROY | 93.98 | 90.03 | 95.79 | 100
17 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Shrinathpur TG water supply scheme, TW no I and II of under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000070/2023-2024 | 1217/NMD-II | 27/06/2023 | 27/07/2023 | JAL PRAVAHIKA PVT. LTD. | 21.6 | 21.33 | 98.76 | 100
18 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Laying distribution system with new HDPE/DI pipeline and other allied works for providing FHTC in connection with the Shrinathpur TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000195/2023-2024 | 1471/ALD | 16/08/2023 | 09/10/2024 | KAMALESH ROY | 32.95 | 30.78 | 93.43 | 100
19 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Supply of CIDF & CISS Pipes and specials for Srinathpur TG WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division,RWS Alipurduar - II Block | ORD/000232/2023-2024 | 1599/ALD | 25/08/2023 | 24/09/2023 | GIRIRAJ ENTERPRISE | 6.7 | 6.56 | 97.9 | 98
20 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Land Development, paver block installation and laying of distribution of UPVC Pipeline at 2nd Pump House site and adjacent area of Shrinathpur TG Area PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000290/2023-2024 | 2014/ALD | 15/09/2023 | 14/11/2023 | SAMIR SARKAR | 6.97 | 2.97 | 42.55 | 100
21 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 142/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 10.48 | 0 | 0 | 0
22 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
23 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Laying distribution system with new HDPE pipeline (Part- B) and providing FHTC and others allied works for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000286/2022-2023 | 1640/ALD | 19/09/2022 | 18/11/2022 | TAPASH KUMAR BHOWMICK | 55.91 | 45.38 | 81.18 | 50
24 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000413/2022-2023 | 2728/ALD | 30/12/2022 | 30/12/2023 | APSARI BHOWMICK | 4.8 | 0 | 0 | 0
25 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Laying of 90 mm HDPE pipeline in uncovered area and construction of excess work of boundary wall and 3 m span open foundation culvert with boulder protection works and other allied works at 2nd site of Shrinathpur TG PWSS under alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000131/2025-2026 | 1628/ALD | 04/08/2025 | 18/10/2025 | PRAPTI DUTTA | 11.82 | 0 | 0 | 0
26 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 | New | Laying distribution system with new HDPE pipeline (Part- C) and providing FHTC and others allied works for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000287/2022-2023 | 1641/ALD | 19/09/2022 | 06/05/2025 | DAS CONSTRUCTION | 58.4 | 54.08 | 92.6 | 45
Total | [13 empty] | 822.15 | 615.99 | 74.92