## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NEPANIA PIPED WATER SUPPLY SCHEME | SM/11766 | Augmentation | Tube well boring by ODEX-195 Method of drilling, Construction of 1no. of Pump house, boundary wall an distribution line with FHTC for Augmentation of NEPANIA PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000348/2022-2023 | 2489/ALD | 13/12/2022 | 12/04/2023 | BHAGWATI BHUJEL | 59.01 | 42.45 | 71.93 | 80
2 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF NEPANIA PIPED WATER SUPPLY SCHEME | SM/11766 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Nepania Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,,Apd | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000913/2023-2024 | 2491/NMD-II | 14/08/2023 | 13/09/2023 | M/S DE ENGINEERING CONCERN | 12.95 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NEPANIA PIPED WATER SUPPLY SCHEME | SM/11766 | Augmentation | Gap filling of HDPE pipeline at Nepania Division area under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000325/2023-2024 | 2422/ALD | 09/11/2023 | 08/01/2024 | BHAGWATI BHUJEL | 5.01 | 5.01 | 99.85 | 100
4 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF NEPANIA PIPED WATER SUPPLY SCHEME | SM/11766 | Augmentation | Quotation for Nepania P/H NO-I |  |  | BILL/02164/2023-2024 |  | 01/12/2023 | 01/12/2023 | WBSEDCL | 28.07 | 0 | 0 | 0
Total | [13 empty] | 105.05 | 47.46 | 45.17