## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Uttar Sishubari PWSS under Alipurduar Division, PHE Dte. Part-4 | Birpara A.E | Alipurduar Sub Division | ORD/000260/2022-2023 | 1492/ALD | 05/09/2022 | 04/12/2022 | MITHUN DAS | 24.32 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Providing FHTC from existing distribution system as per specification for UTTAR SISHUBARI PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000284/2023-2024 | 1991/ALD | 15/09/2023 | 14/12/2023 | MITHUN DAS | 57.24 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Construction of pump house, Boundary Wall, Tube well Boring (by ODEX-165 method of drilling) and Rising main, laying of DI and UPVC pipeline for Uttar Sishubari PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000041/2023-2024 | 387/ALD | 19/05/2023 | 10/09/2024 | MITHUN DAS | 93.44 | 40.47 | 43.31 | 62
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Construction of Tubewell by ODEX-165 method of drilling at HWS, construction of pump house and boundary wall at HWS, laying of rising main for Aug. Of Uttar Sishubari PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000473/2023-2024 | 691/ALD | 07/03/2024 | 21/04/2024 | MITHUN DAS | 31.88 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Soil investigation at OHR site and construction of 450cum OHR at Uttar Sishubari under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000197/2024-2025 | 1767/ALD | 07/06/2024 | 03/04/2025 | BISWAJIT DUTTA | 118.67 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Laying of distribution pipe in Uttar Sishubari Bazar area and Madarihat Bazar Area and allied works Under Birpara Sub-division, Alipurduar Division PHE DTE. | Birpara A.E |  | ORD/000396/2022-2023 | .2663/ALD | 22/12/2022 | 21/04/2023 | MITHUN DAS | 25.68 | 25.17 | 98.01 | 100
7 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR UTTAR SISHUBARI MADARIHAT GOPAL BAGAN PWSS |  |  | BILL/00630/2024-2025 | BP-170/24-25 | 03/07/2024 | 03/07/2024 | WBSEDCL | 5.41 | 0 | 0 | 0
8 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of UTTAR SISHUBARI Water Supply Scheme TWNo- I AND II under NMDII,PHE.Dte,APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001143/2023-2024 | 2887/NMD-II | 17/10/2023 | 17/11/2025 | S.D CONCERN WORKSHOP | 22.02 | 0 | 0 | 45
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Birpara A.E | Birpara Sub Division | ORD/000080/2025-2026 | 1048/ALD | 17/06/2025 | 16/08/2025 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
Total | [13 empty] | 471.16 | 65.64 | 13.93