## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11960 | Augmentation | Soil investigation work for proposed overhead reservoir, cons. Of 150cum OHR at Dalmore, 2nos. Of TW boring by ODEX-165 method of drilling at Dalmore and Ramjhora, cons. of pump house and boundary wall at both TW site, LDS as per Departmental Design & drawing for DALMORE & RAMJHORA TG PWSS under Birpara Sub-Division, Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000131/2023-2024 | 638/ALD | 06/06/2023 | 03/12/2023 | SUKAMAL GHOSH | 158.82 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11960 | Augmentation | Providing FHTC from existing distribution system as per specification for DALMORE RAMJHORA PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000293/2023-2024 | 2024/ALD | 19/09/2023 | 18/11/2023 | SUDDHYA SING LAMA | 23.76 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11960 | Augmentation | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | Birpara A.E | RWS Falakata Block | ORD/000417/2022-2023 | 2732/ALD | 30/12/2022 | 30/12/2023 | PARITOSH SUTRADHAR | 4.8 | 0 | 0 | 90
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11960 | Augmentation | Soil investigation work for proposed overhead reservoir , Constructions of 150 Cum OHR at HW site and providing FHTC as per Departmental Design & drawing for Ramjhora PWSS Under Birpara Sub-division, Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000398/2022-2023 | 2661/ALD | 22/12/2022 | 13/08/2024 | SUDDHYA SING LAMA | 91.76 | 0 | 0 | 90
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11960 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 3610/ALD | 24/10/2024 | 24/10/2024 | Resource Division | 11.11 | 0 | 0 | 0
6 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11960 | Augmentation | New Service Connection Charges for Dalmore & Ramjhora TG PH NO-IV |  |  | BILL/01584/2024-2025 | BP-412/24-25 | 20/11/2024 | 20/11/2024 | WBSEDCL | 6.75 | 0 | 0 | 0
7 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11960 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR DALMORE& RAMJHORA T.G P/H NO-V PWSS |  |  | BILL/02452/2023-2024 | BP-2023-24-550 | 18/01/2024 | 18/01/2024 | WBSEDCL | 5.99 | 0 | 0 | 0
8 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11960 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME,TW No.- I of Zone-I AND II under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001234/2023-2024 | 2968/NMD-II | 21/11/2023 | 04/03/2025 | B.B CONCERNED | 28.76 | 0 | 0 | 90
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11960 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11960 | Augmentation | Laying of additional HDPE pipeline at Ramjhora TG under Ranjhora WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000128/2025-2026 | 1536/ALD | 29/07/2025 | 12/09/2025 | SUNIL HAJANG THAKUR | 13.14 | 0 | 0 | 0
Total | [13 empty] | 419.24 | 0 | 0