## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Kumargram PWSS, Kumargram Block under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000170/2022-2023 | 1009/ALD | 15/07/2022 | 13/09/2022 | DILIP MAHATO | 43.79 | 13.32 | 30.41 | 6
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Providing House connection for KUMARGRAM water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. |  |  | ORD/000141/2020-2021 | 857/ALD | 14/10/2020 | 13/11/2020 | ASHIM KUMAR CHAKRABORTY | 4.98 | 4.98 | 100 | 8
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000474/2021-2022 | 2764/ALD | 25/02/2022 | 26/04/2022 | TAPAN CHANDA | 50.32 | 11.6 | 23.06 | 60
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Restoration of Laying distribution system by replacing of Damaged AC pipeline with UPVC pipe of Kumargram WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000153/2022-2023 | 1004/ALD | 15/07/2022 | 14/08/2022 | DILIP MAHATO | 4.92 | 4.65 | 94.5 | 8
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | NEW CONNECTION FOR TUTURIKHANDA |  |  | BILL/00044/2022-2023 | 394/22-23/PFMS | 21/12/2022 | 21/12/2022 | WBSEDCL | 0.08 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Soil investigation work at 4 different places of Kumargram within Alipurduar District under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000264/2022-2023 | 1502/ALD | 05/09/2022 | 05/10/2022 | MOYTEC | 4.88 | 4.88 | 100 | 7
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Repairing and renovation of pump house, boundary wall and construction of new toilet of 2nd T/W site at Kumargram Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000306/2022-2023 | 1944/ALD | 17/10/2022 | 16/12/2022 | TAPASH DAS | 4.73 | 3.99 | 84.46 | 8
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Preparation of detailed Additional cost Requirement D.P.R. booklets in connection to various PWSS under Kumargram and Kalchini Block under Alipurduar Division P.H.E Dte. | HQ-A.E | Alipurduar Sub Division | ORD/000186/2023-2024 | 1204/ALD | 07/08/2023 | 06/09/2023 | ANIK BHATTACHARJEE | 0.78 | 0.78 | 100 | 100
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 1702/ALD | 21/09/2022 | 21/09/2022 | Resource Division | 61.6 | 0 | 0 | 0
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 3483/ALD | 23/03/2023 | 23/03/2023 | Resource Division | 61.6 | 0 | 0 | 0
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 2721/ALD | 13/12/2023 | 13/12/2023 | Resource Division | 97.75 | 0 | 0 | 0
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Tube well boring by ODEX-165, Construction of pump house and boundary wall including laying distribution system with new UPVC pipeline with rising and delivery line connection, Providing FHTC and other allied works for KUMARGRAM PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000464/2022-2023 | 3000/ALD | 06/02/2023 | 05/08/2023 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 1152.29 | 660 | 57.28 | 50
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Laying of rising main line /distribution pipeline, supply of DI pipe and specials, horizontal boring by HDD method, bridge and culvert crossing, specials repair with trial run of pipeline and allied works at Aug. of Kumargram WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000471/2023-2024 | 689/ALD | 07/03/2024 | 02/12/2024 | HARI CONSTRUCTION | 40.9 | 0 | 0 | 0
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Construction of 250cum OHR for KUMARGRAM ZONE-I Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000258/2022-2023 | 1489/ALD | 05/09/2022 | 25/08/2024 | GOUTAM KUMAR DAS | 57.3 | 52.88 | 92.28 | 95
15 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Construction of 150cum. OHR for KUMARGRAM ZONE-IV Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000255/2022-2023 | 1486/ALD | 05/09/2022 | 04/03/2023 | MATRI ENTERPRISE | 50.41 | 46.14 | 91.54 | 100
16 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Construction of OHR 200cum for KUMARGRAM ZONE-II Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000256/2022-2023 | 1487/ALD | 05/09/2022 | 04/03/2023 | S.G ENTERPRISE | 55.09 | 46.61 | 84.61 | 100
17 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Construction of OHR 200cum for KUMARGRAM ZONE-III Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000257/2022-2023 | 1488/ALD | 05/09/2022 | 25/08/2024 | UNIVERSAL ENTERPRISES | 55.33 | 47.63 | 86.07 | 100
18 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2024-2025 | 3950/ALD | 26/11/2024 | 26/11/2024 | Resource Division | 12.32 | 0 | 0 | 0
19 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | New Service Connection Charges for AUGMENTATION OF KUMARGRAM (Uttar Haldibari) pwss ph NO-I Zone-III |  |  | BILL/00891/2024-2025 | BP-289/24-25 | 22/08/2024 | 22/08/2024 | WBSEDCL | 3.22 | 0 | 0 | 0
20 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | New Service Connection Charges for AUGMENTATION OF KUMARGRAM (AMARPUR) pwss PH NO-I Zone-IV |  |  | BILL/00892/2024-2025 | BP-290/24-25 | 22/08/2024 | 22/08/2024 | WBSEDCL | 5.75 | 0 | 0 | 0
21 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | New service connection charges for Aug of Kumargram Z-I, P/H-I under NMD-II |  |  | BILL/01899/2024-2025 | BP-443/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 6.26 | 0 | 0 | 0
22 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
23 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | New service connection charges for AUG of Kumargram Zone-IV, P/H-II(Amarpur) under NMD-II |  |  | BILL/01895/2024-2025 | BP-443/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 7.59 | 0 | 0 | 0
24 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | New Service Connection Charges for AUGMENTATION OF KUMARGRAM (Uttar Haldibari) pwss PH NO-II Zone-III |  |  | BILL/00890/2024-2025 | BP-288/24-25 | 22/08/2024 | 22/08/2024 | WBSEDCL | 4.46 | 0 | 0 | 0
25 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR MADHYA HALDIBARI PWSS ZONE-II P/H NO-II |  |  | BILL/02803/2023-2024 | BP-2023-24-642 | 29/02/2024 | 29/02/2024 | WBSEDCL | 12.17 | 0 | 0 | 0
26 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | NEW SERVICE CONNECTION FOR MADHYA HALDIBARI PWSS ZONE-II P/H NO-I |  |  | BILL/02802/2023-2024 | BP-2023-24-643 | 29/02/2024 | 29/02/2024 | WBSEDCL | 6.22 | 0 | 0 | 0
27 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of KUMARGRAM Water Supply Scheme TW No.-I,II,III,IV,V,VI,VII and VIII under NMD-II,PHE.Dte,APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000926/2023-2024 | 2512/NMD-II | 14/08/2023 | 20/11/2025 | ALPHA ENTERPRISE | 93.39 | 0 | 0 | 70
28 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte..(from 01.02.2024 to 31.01.2025) | Alipurduar Sadar Sub Division,HQ-A.E | Birpara Sub Division | ORD/000500/2023-2024 | 372/ALD | 31/01/2024 | 31/01/2025 | CHANDAN KIRTONIA | 4.8 | 4.25 | 88.52 | 0
29 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Repairing of Kumargram Rest Shed and other works at Kumargram PWSS, Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. (SM/11985) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000450/2024-2025 | 5062/ALD | 18/02/2025 | 04/04/2025 | DULAL DAS | 3.09 | 0 | 0 | 0
30 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
31 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | SM/11985 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kumargram Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000081/2025-2026 | 1049/ALD | 17/06/2025 | 16/08/2025 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
Total | [13 empty] | 2062.53 | 901.71 | 43.72