## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | SM/11991 | New | Soil investigation works for proposed overhead reservoir of KARTIKA TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000315/2022-2023 | 2224/ALD | 21/11/2022 | 21/12/2022 | K S GROUP | 0.65 | 0.65 | 100 | 0
2 | ALIPURDUAR | Kumargram | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | SM/11991 | New | Laying distribution system with new DI line and Supply of necessary specials, construction of sluice valve chamber, Construction of pump house and boundary wall at 2nd site of Kartika TG Area PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,Birpara Sub Division | ORD/000338/2022-2023 | 2247/ALD | 21/11/2022 | 21/03/2023 | MONORAMA ENTERPRISE | 10.8 | 9.7 | 89.88 | 78
3 | ALIPURDUAR | Kumargram | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | SM/11991 | New | Tube well Boring by ODEX-165 method at 2nd TW Site, Cons. of Pump house and boundary wall at HW site, LDS with new HDPE pipeline (Part-B) with Rising Main and delivery line connection, providing FHTC and other allied works for Kartika Tea Garden PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000330/2022-2023 | 2239/ALD | 21/11/2022 | 21/03/2023 | TAPASH DAS | 79.55 | 66.61 | 83.74 | 84
4 | ALIPURDUAR | Kumargram | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | SM/11991 | New | Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Construction of 200 cum OHR as per Departmental Design & drawing, Providing FHTC and other allied works for KARTIKA TEA GARDEN PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000455/2022-2023 | 2976/ALD | 02/02/2023 | 21/07/2025 | MAHENDRA CHHETRI | 238.07 | 191.37 | 80.39 | 90
5 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | SM/11991 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Kartika TG water supply scheme, TW no I and II of under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000676/2023-2024 | 2085/NMD-II | 26/07/2023 | 25/08/2023 | DIAMOND ELECTRICAL WORKS | 18.63 | 17.89 | 96 | 90
6 | ALIPURDUAR | Kumargram | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | SM/11991 | New | Supply of CIDF & CISS Pipes and specials for Kartika TG WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000223/2023-2024 | 1594/ALD | 25/08/2023 | 24/09/2023 | JUGAL CHOUDHURY | 6.76 | 5.59 | 82.67 | 68
7 | ALIPURDUAR | Kumargram | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | SM/11991 | New | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 217/ALD | 03/05/2023 | 03/05/2023 | Resource Division | 18.8 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | SM/11991 | New | Quotation for NSC at P/H No.II under Kartika TG Area W/S/S |  |  | BILL/00603/2023-2024 | BP-2023-24-171 | 15/06/2023 | 15/06/2023 | WBSEDCL | 1.31 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | SM/11991 | New | Quotation for NSC at P/H No.I under Kartika TG Area W/S/S |  |  | BILL/00602/2023-2024 | BP-2023-24-170 | 15/06/2023 | 15/06/2023 | WBSEDCL | 1.31 | 0 | 0 | 0
10 | ALIPURDUAR | Kumargram | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | SM/11991 | New | Supply of DI specials and CI Jeffy coupling for Kartika TG Water Supply Scheme (SM/11991) of Kumargram Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000522/2023-2024 | 841/ALD | 14/03/2024 | 13/04/2024 | MANSAROVAR CASTING | 13.34 | 13.34 | 100 | 92
11 | ALIPURDUAR | Kumargram | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | SM/11991 | New | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 134/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 6.95 | 0 | 0 | 0
12 | ALIPURDUAR | Kumargram | Alipurduar Division | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | SM/11991 | New | Repairing and relaying of 90 mm dia damaged HDPE pipeline (from node-33 to 32 to 29 to 25) for Kartika PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000169/2025-2026 | 1777/ALD | 18/08/2025 | 02/10/2025 | TAPASH DAS | 1.4 | 0 | 0 | 0
Total | [13 empty] | 397.57 | 305.16 | 76.76