## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | Laying distribution system with new HDPE and DI pipeline, Supply of necessary specials, construction of sluice valve chamber, boundary wall at 2nd site of RAYDAK TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000323/2022-2023 | 2232/ALD | 21/11/2022 | 19/02/2023 | ALATYA CONSTRUCTION & CO. | 13.65 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | Laying distribution system with new HDPE and DI pipeline, Supply of necessary specials, construction of sluice valve chamber, boundary wall at Head work site of RAYDAK TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,Birpara Sub Division | ORD/000325/2022-2023 | 2234/ALD | 21/11/2022 | 19/02/2023 | HITANGSHU CHOUDHURY | 15.63 | 0 | 0 | 61
3 | ALIPURDUAR | Kumargram | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | Laying of new HDPE pipe line, Construction of Pump House at Head Work Site and providing FHTC and other allied works for Raydak TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,Birpara Sub Division | ORD/000320/2022-2023 | 2229/ALD | 21/11/2022 | 21/03/2023 | CREATIVE UN EMPLOYED ENGINEERSCO OPER SOCYLIMITED | 13.78 | 0 | 0 | 61
4 | ALIPURDUAR | Kumargram | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | Soil investigation works for proposed overhead reservoir of RAYDAK TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000313/2022-2023 | 2222/ALD | 21/11/2022 | 21/12/2022 | K S GROUP | 0.65 | 0.65 | 100 | 0
5 | ALIPURDUAR | Kumargram | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | Tube well Boring by ODEX-165 method of drilling at 2nd TW Site, Construction of Pump house at 2nd site, laying of Rising Main and delivery line connection, providing FHTC and other allied works for RAYDAK Tea Garden PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000328/2022-2023 | 2237/ALD | 21/11/2022 | 13/07/2024 | DAS CONSTRUCTION | 95.24 | 52.81 | 55.45 | 65
6 | ALIPURDUAR | Kumargram | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Construction of 300 cum OHR as per Departmental Design & drawing, Providing FHTC and other allied works for RAYDAK TEA GARDEN PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000457/2022-2023 | 2978/ALD | 02/02/2023 | 01/08/2023 | CHINMOY BHATTACHARJEE | 233.78 | 107.45 | 45.96 | 54
7 | ALIPURDUAR | Kumargram | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | Laying of new HDPE pipeline in the balance portion distribution system of Raydak TG PWSS under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000008/2023-2024 | 92/ALD | 18/04/2023 | 17/06/2023 | TILAK SHARMA | 12.11 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | Laying of new HDPE pile line in the balance portion distribution system at Sanialine & adj. Area of Raydak TG PWSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000031/2023-2024 | 362/ALD | 18/05/2023 | 17/07/2023 | SUMAN CHAKRABORTY | 7.99 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | Tubewell boring by ODEX-165 method of drilling, construction of Pump House, Boundary Wall at Proposed 3rd TW site of Raydak TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000032/2023-2024 | 363/ALD | 18/05/2023 | 12/05/2024 | POLY CONSTRUCTION | 17.71 | 0 | 0 | 3
10 | ALIPURDUAR | Kumargram | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | Laying of new HDPE pile line in the balance portion distribution system at khuruline & four line of Raydak TG PWSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000038/2023-2024 | 369/ALD | 18/05/2023 | 17/07/2023 | PRAPTI DUTTA | 10 | 4.26 | 42.57 | 80
11 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Raydak TG water supply scheme, TW no I,II and III of under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000039/2023-2024 | 998/NMD-II | 16/05/2023 | 15/06/2023 | DEY ENTERPRISE (BALLY) | 28.63 | 0 | 0 | 90
12 | ALIPURDUAR | Kumargram | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | Providing balance FHTC for Raydak TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000207/2023-2024 | 1561/ALD | 23/08/2023 | 07/10/2023 | BRAJA GOPAL SAHA | 6.69 | 0 | 0 | 0
13 | ALIPURDUAR | Kumargram | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | Supply of DI specials and CI Jeffy coupling for Raydak TG Water Supply Scheme(SM/12114) of Kumargram Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000516/2023-2024 | 835/ALD | 14/03/2024 | 11/08/2024 | HARI CONSTRUCTION | 15.18 | 0 | 0 | 80
14 | ALIPURDUAR | Kumargram | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | Supply of CIDF & CISS Pipes and specials for Raydak TG WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000224/2023-2024 | 1595/ALD | 25/08/2023 | 24/09/2023 | DAS CONSTRUCTION | 6.76 | 3.37 | 49.83 | 95
15 | ALIPURDUAR | Kumargram | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 129/ALD | 10/01/2024 |  | Resource Division | 12.31 | 0 | 0 | 0
16 | ALIPURDUAR | Kumargram | Alipurduar Division | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 207/ALD/2023-2024 | 02/05/2023 |  | Resource Division | 44.73 | 0 | 0 | 0
17 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | New Service Connection at Raydak TG p/h-III |  |  | BILL/00749/2023-2024 | BP-2023-24-191 | 22/06/2023 |  | WBSEDCL | 1.31 | 0 | 0 | 0
18 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | New Service Connection at Raydak TG p/h-I |  |  | BILL/00747/2023-2024 | BP-2023-24-193 | 22/06/2023 |  | WBSEDCL | 1.31 | 0 | 0 | 0
19 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | New Service Connection at Raydak TG p/h-II |  |  | BILL/00748/2023-2024 | BP-2023-24-192 | 22/06/2023 |  | WBSEDCL | 1.31 | 0 | 0 | 0
20 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | ADDITIONAL QUOTATION FOR RAYDAK T.G P/H NO-II |  |  | BILL/02956/2023-2024 | BP-2023-24-682 | 12/03/2024 |  | WBSEDCL | 4.7 | 0 | 0 | null
21 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | ADDITIONAL QUOTATION FOR RAYDAK T.G P/H NO-II |  |  | BILL/02956/2023-2024 | BP-2023-24-682 | 12/03/2024 |  | WBSEDCL | 4.7 | 0 | 0 | null
22 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | ADDITIONAL QUOTATION FOR RAYDAK P/H NO-III |  |  | BILL/02957/2023-2024 | BP-162/24-25 | 21/06/2024 |  | WBSEDCL | 5.9 | 0 | 0 | null
23 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 | New | ADDITIONAL QUOTATION FOR RAYDAK P/H NO-III |  |  | BILL/02957/2023-2024 | BP-162/24-25 | 21/06/2024 |  | WBSEDCL | 5.9 | 0 | 0 | null
Total | [13 empty] | 559.97 | 168.54 | 30.1