## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Providing balance FHTC from existing distribution system as per specification for HASIMARA PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000283/2023-2024 | 1990/ALD | 15/09/2023 | 14/12/2023 | BRAJA GOPAL SAHA | 73.9 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Special repairing of road for providing of FHTC at Northen side of Hasimara PWSS under Alipurduar, Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000313/2023-2024 | 2178/ALD | 06/10/2023 | 05/11/2023 | SHIB RATAN BHOWMIK | 0.93 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Soil investigation work at proposed OHR construction site of Hasimara PWSS under Alipurduar Division PHE Dte. | HQ-A.E |  | ORD/000405/2022-2023 | 2790/ALD | 10/01/2023 | 09/02/2023 | MOYTEC | 0.95 | 0 | 0 | 100
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 185/ALD | 28/04/2023 | 28/04/2023 | Resource Division | 33.51 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Construction of 700cum OHR for Augmentation of HASIMARA Water Supply Scheme under Alipurduar Division, PHE Dte.(3rd call) | HQ-A.E | RWS Kalchini Block | ORD/000479/2022-2023 | 3196/ALD | 27/02/2023 | 26/08/2023 | BRAJA GOPAL SAHA | 121.92 | 0 | 0 | 90
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Laying of DI & HDPE pipeline from Santali TG and Malangi TG to the existing OHR at Hasimara PWSS area, kalchini Block under Alipurduar division, PHE Dte. | HQ-A.E | Birpara Sub Division,RWS Kalchini Block,RWS Kumargram Block | ORD/000042/2023-2024 | 388/ALD | 19/05/2023 | 04/03/2026 | D. K. & SONS | 26.33 | 0 | 0 | 100
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Continuation of work of "Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Deputy Superintending Engineer, North Bengal Circle-I , P.H.E. Dte.(from 01.03.2024 to 31.07.2024)" | HQ-A.E |  | ORD/000549/2023-2024 | 602/ALD | 27/02/2024 | 27/07/2024 | MAHENDRA CHHETRI | 2 | 0 | 0 | 0
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Continuation order for the work of "Collection of house hold details at prescribed format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same to PHE Dte. (in soft copy) Part-B" | Alipurduar Sadar Sub Division | Alipurduar Sub Division,Birpara Sub Division | ORD/000346/2024-2025 | 3424/ALD | 26/09/2024 | 26/03/2025 | TAPASH KUMAR BHOWMICK | 4.67 | 0 | 0 | 100
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 3611/ALD | 24/10/2024 | 24/10/2024 | Resource Division | 9.89 | 0 | 0 | 0
10 | ALIPURDUAR |  | Central Drilling | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Restoration of pipeline for Gap filling and other allied works under Hasimara PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kumargram Block | ORD/000453/2024-2025 | 5170/ALD | 25/02/2025 | 26/04/2025 | BRAJA GOPAL SAHA | 4.47 | 0 | 0 | 0
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Construction of 1no. Pump House boundary wall, at new Hasimara PWSS Area under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kumargram Block | ORD/000454/2024-2025 | 5171/ALD | 25/02/2025 | 25/06/2025 | BRAJA GOPAL SAHA | 17.18 | 0 | 0 | 0
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Reparing of Pump House at Headwork site of HASIMARA PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000598/2024-2025 | 5427/ALD | 19/03/2025 | 18/05/2025 | DOOARS SOCIAL WELFARE ORGANISATION | 0.78 | 0 | 0 | 0
15 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kalchini Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | HQ-A.E | RWS Kalchini Block | ORD/000084/2025-2026 | 1052/ALD | 17/06/2025 | 16/08/2025 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
16 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Construction of deep TW by ODEX-165 method of drilling for Subhashini TG under Hasimara PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kumargram Block | ORD/000099/2025-2026 | 1184/ALD | 26/06/2025 | 25/08/2025 | SWARAN ENTERPRISE | 8.73 | 0 | 0 | 0
17 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Continuation for the work of Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000023/2025-2026 | 343/ALD | 29/04/2025 | 26/10/2025 | TAPASH KUMAR BHOWMICK | 4.29 | 0 | 0 | 0
18 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Reparing of Pump House at 3rd site of MADHU TG PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000139/2025-2026 | 1576/ALD | 31/07/2025 | 29/09/2025 | NARENDRA BHADANI. | 0.78 | 0 | 0 | 0
19 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Reparing of Pump House at Headwork site of MADHU TG PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000140/2025-2026 | 1577/ALD | 31/07/2025 | 29/09/2025 | NARENDRA BHADANI. | 0.94 | 0 | 0 | 0
20 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Continuation for the work of hiring of diesel vehicle maxi cab (At least 7 seater) for Deputy Superintending Engineer, North Bengal Circle-I, P.H.E. Dte. (from 01.03.2024 to 31.10.2024) | HQ-A.E | Alipurduar Sub Division | ORD/000555/2023-2024 | 620/ALD | 29/02/2024 | 31/10/2024 | MAHENDRA CHHETRI | 3.2 | 0 | 0 | 0
21 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Reparing of Pump House at 2nd site of MADHU TG PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000138/2025-2026 | 1575/ALD | 31/07/2025 | 29/09/2025 | NARENDRA BHADANI. | 0.94 | 0 | 0 | 0
22 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Restoration of pipeline and FHTC and allied works at Madhu TG under Augmentation of Hasimara PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kumargram Block | ORD/000196/2025-2026 | 2103/ALD | 23/09/2025 | 22/11/2025 | NARENDRA BHADANI. | 6.46 | 0 | 0 | 0
23 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Painting of Old OHR of 300 cum at Madhu under Augmentation of Hasimara PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kumargram Block | ORD/000197/2025-2026 | 2104/ALD | 23/09/2025 | 22/11/2025 | NARENDRA BHADANI. | 3.39 | 0 | 0 | 0
24 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Continuation for the work of "Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. " | Alipurduar Sadar Sub Division | Alipurduar Sub Division,Birpara Sub Division | ORD/000347/2024-2025 | 3425/ALD | 26/09/2024 | 26/03/2025 | TAPASH KUMAR BHOWMICK | 4.29 | 0 | 0 | 100
25 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Construction of a pump house at Old Hasimara HW Site PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block,RWS Kumargram Block | ORD/000476/2023-2024 | 694/ALD | 07/03/2024 | 22/03/2025 | AMIT BARDHAN | 7.2 | 0 | 0 | 100
Total | [13 empty] | 21768.99 | 0 | 0