## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | SISHA JUMRHA PIPED WATER SUPPLY SCHEME | SM/12753 | New | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 1275/ALD | 11/08/2023 | 11/08/2023 | Resource Division | 54.68 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | SISHA JUMRHA PIPED WATER SUPPLY SCHEME | SM/12753 | New | NEW SERVICE CONNECTION FOR SISHUJHUMRA PWSS P/H NO-I,BIRPARA,ALIPURDUAR, APPLICATION NO 4003068997 |  |  | BILL/01783/2023-2024 | BP-2023-24-366 | 27/09/2023 | 27/09/2023 | WBSEDCL | 6.89 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | SISHA JUMRHA PIPED WATER SUPPLY SCHEME | SM/12753 | New | NEW SERVICE CONNECTION FOR SISHUJHUMRA PWSS,P/H NO II,BIRPARA,ALIPURDUAR, APPLICATION NO 4003068181 |  |  | BILL/01784/2023-2024 | BP-2023-24-365 | 27/09/2023 | 27/09/2023 | WBSEDCL | 9.33 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | SISHA JUMRHA PIPED WATER SUPPLY SCHEME | SM/12753 | New | NEW SERVICE CONNECTION FOR SISHUJHUMRA PWSS,P/H NO- III,BIRPARA, ALIPURDUAR, APPLICATION NO 4003068999 |  |  | BILL/01785/2023-2024 | BP-2023-24-364 | 27/09/2023 | 27/09/2023 | WBSEDCL | 6.65 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Alipurduar Division | SISHA JUMRHA PIPED WATER SUPPLY SCHEME | SM/12753 | New | Construction of boulder apron for Dimdima PWSS in sishujhumra mouza for protection of existing HW site under Alipurduar Division. | Birpara A.E | Birpara Sub Division | ORD/000487/2023-2024 | 743/ALD | 12/03/2024 | 25/07/2024 | SUBIR GHOSH | 4.03 | 0 | 0 | 10
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | SISHA JUMRHA PIPED WATER SUPPLY SCHEME | SM/12753 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SISHU JUMRHA water supply scheme, TW no I , II and III under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000787/2023-2024 | 2357/NMD-II | 07/08/2023 | 06/09/2023 | GEETA CONSTRUCTION | 27.96 | 0 | 0 | 100
7 | ALIPURDUAR | Madarihat | Alipurduar Division | SISHA JUMRHA PIPED WATER SUPPLY SCHEME | SM/12753 | New | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 113/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 16.53 | 0 | 0 | 0
8 | ALIPURDUAR | Madarihat | Alipurduar Division | SISHA JUMRHA PIPED WATER SUPPLY SCHEME | SM/12753 | New | 3 nos. of Tube well Boring by ODEX-165 Method of drilling at HW site, 2nd TW and 3rd site site and Constructions of 350 Cum OHR at HW site inclu. soil testing , construction of pump house and boundary wall at H/W, 2nd site and 3rd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for SISHA JUMRHA PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000555/2022-2023 | 3576/ALD | 27/03/2023 | 14/09/2025 | DILIP MAHATO | 539.73 | 0 | 0 | 23
9 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | SISHA JUMRHA PIPED WATER SUPPLY SCHEME | SM/12753 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
10 | ALIPURDUAR | Madarihat | Alipurduar Division | SISHA JUMRHA PIPED WATER SUPPLY SCHEME | SM/12753 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Birpara A.E | Birpara Sub Division | ORD/000080/2025-2026 | 1048/ALD | 17/06/2025 | 16/08/2025 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
11 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | SISHA JUMRHA PIPED WATER SUPPLY SCHEME | SM/12753 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini, Madarihat -Birpara ,kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000131/2025-2026 | 1332/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
Total | [13 empty] | 1437.38 | 0 | 0