## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 3044/ALD | 08/02/2023 | 08/02/2023 | Resource Division | 21.01 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | NEW SERVICE CONNECTION CHARGE FOR PURBA KHALISHAMARI W/S/S P/H NO.2 |  |  | BILL/00593/2023-2024 | BP-2023-24-182 | 15/06/2023 | 15/06/2023 | WBSEDCL | 1.41 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | NEW SERVICE CONNECTIO CHARGE FOR PURBA KHALISHAMARI W/S/S P/H NO.1 |  |  | BILL/00592/2023-2024 | BP-2023-24-181 | 15/06/2023 | 15/06/2023 | WBSEDCL | 1.41 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Constructions of pump house & Sinking of 250 mm x 200 mm X 150 mtr. Big dia. Tube well at HW site & 2nd site , laying of distribution system with UPVC pipeline , Constructions of 250 Cum OHR as per Departmental Design & drawing including soil test, providing FHTC and others allied works for Purba Khalisamari PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000557/2022-2023 | 3577/ALD | 27/03/2023 | 14/07/2025 | HARIDAS GHOSH | 438.25 | 358.4 | 81.78 | 72
5 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Supply of CIDF & CISS Pipes and specials for Purba Khalshamari WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,Birpara Sub Division | ORD/000229/2023-2024 | 1604/ALD | 25/08/2023 | 24/09/2023 | HARI CONSTRUCTION | 6.76 | 0 | 0 | 100
6 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing, Land development works, construction of surface drain, pathway, trial run and others allied works in connection with the Purba Khailshmari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000397/2024-2025 | 4236/ALD | 12/12/2024 | 10/02/2025 | HARI CONSTRUCTION | 75.41 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PURBA KHALISHAMARI water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000793/2023-2024 | 2365/NMD-II | 08/08/2023 | 07/09/2023 | MENAKA ENTERPRISE | 21.73 | 21.5 | 98.92 | 100
8 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Supply of CIDF/CIPE Pipes and Special & CI Jeffy Coupling for Purba Khalishamari Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000481/2023-2024 | 699/ALD | 07/03/2024 | 06/04/2024 | HARI CONSTRUCTION | 15.31 | 15.31 | 100 | 70
9 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 106/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 11.82 | 0 | 0 | 0
10 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 3613/ALD | 24/10/2024 | 24/10/2024 | Resource Division | 7.78 | 0 | 0 | 0
11 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Material Requisition To Resource Division |  |  | RTOR000053/2024-2025 | 4273/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 11.33 | 0 | 0 | 0
12 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
13 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
14 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
15 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Solarization of grid connected pumping installation at different PWSS at Alipurduar -II block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001205/2024-2025 | 819/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
16 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Material Requisition To Resource Division |  |  | RTOR000005/2025-2026 | 1564/ALD | 31/07/2025 | 31/07/2025 | Resource Division | 5.02 | 0 | 0 | 0
17 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Material Requisition To Resource Division |  |  | RTOR000013/2025-2026 | 2037/ALD | 15/09/2025 | 15/09/2025 | Resource Division | 6.28 | 0 | 0 | 0
Total | [13 empty] | 1516.98 | 395.2 | 26.05