## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Providing FHTC from existing distribution system as per specification for Nimti Domohani PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000267/2023-2024 | 1885/ALD | 07/09/2023 | 07/10/2023 | DEBAJYOTI SUTRADHAR | 5.22 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Supply of DIDF pipes and DI specials and CI Jeffy Coupling for Nimtijhora Domohoni Water Supply Scheme (SM/13244) of Kalchini Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000215/2024-2025 | 2067/ALD | 12/07/2024 | 11/08/2024 | MANSAROVAR CASTING | 9.63 | 0 | 0 | 100
3 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Supply of DI specials and CI Jeffy coupling for Nimjhora TG Water Supply Scheme(SM/14215) of Kalchini Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000535/2023-2024 | 851/ALD | 14/03/2024 | 13/04/2024 | MANSAROVAR CASTING | 13.34 | 0 | 0 | 50
4 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 105/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 9.02 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | New Service connection for Nimti Jhora Domohani PWSS, P/H no.-II |  |  | BILL/02410/2023-2024 | BP-2023-24-531 | 11/01/2024 | 11/01/2024 | WBSEDCL | 6.47 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | New Service Connection for Nimti Jhora Domohani PWSS P/H NO-I |  |  | BILL/02307/2023-2024 | BP-2023-24-505 | 05/01/2024 | 05/01/2024 | WBSEDCL | 5.68 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Construction of 2 nos. Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Construction of 200 cum OHR as per Departmental Design & drawing, Pump House , Boundary Wall, Path way including soil test, Providing FHTC and other allied works for NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000548/2022-2023 | 3571/ALD | 27/03/2023 | 19/07/2024 | DOOARS CONSTRUCTION COMPANY | 446.14 | 104.66 | 23.46 | 90
8 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Nimti Domohini Water Supply Scheme TWNo-I and II under NMD-II,PHE.Dte,APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001178/2023-2024 | 2909/NMD-II | 31/10/2023 | 15/05/2025 | GURUKRIPA ENTERPRISE | 21.48 | 0 | 0 | 50
9 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Balance portion of 110 mm HDPE/DI pipe laying, boundary wall, pump house, land development for HWS and 1st site and platform for FHTC for Nimti Domohoni PWSS Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000475/2023-2024 | 693/ALD | 07/03/2024 | 30/05/2025 | PINTU SAHA | 79.36 | 0 | 0 | 30
10 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001209/2024-2025 | 823/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
11 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | 1 Nos TW boring of ODEX-165 for additional T/W for 3rd site of Nimti Domohani PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000069/2025-2026 | 967/ALD | 12/06/2025 | 12/07/2025 | CHINMOY BHATTACHARJEE | 8.07 | 0 | 0 | 0
12 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Yard lighting arrangement at Head Work Site for Different PWSS (NIMTI DOMOHANI and Others) under JJM in the BLOCK: Kalchini, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000170/2025-2026 | 1386/NMD-II | 26/06/2025 | 26/07/2025 | AMUSAR IMPEX PVT LTD | 22.95 | 0 | 0 | 0
13 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
14 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Nimti Domohini Water Supply Scheme TW No.-III (Additional) under NMD-II,PHE.Dte,Alipurduar. | HQ-A.E | JUNIOR ENGINEER | ORD/000058/2025-2026 | 786/ALD | 30/05/2025 | 29/06/2025 | MADHAB SAHA. | 10.8 | 0 | 0 | 0
15 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Construction of 1no Pump house, boundary wall and other allied works at 3rd TW Site of Nimti Domohani PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000163/2025-2026 | 1771/ALD | 18/08/2025 | 16/12/2025 | SATYABRATA BHATTACHERJEE | 21.28 | 0 | 0 | 0
Total | [13 empty] | 1414.52 | 104.66 | 7.4