## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL AND SECOND TUBE WELL site including laying distribution system with new HDPE pipeline (Part-B) CONSTRUCTION OF THREE (3) NOS PUMP HOUSES ,providing FHTC and others allied works for PASCHIM SATALI PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block,RWS Kumargram Block | ORD/000432/2022-2023 | 2859/ALD | 17/01/2023 | 31/01/2026 | MAHENDRA CHHETRI | 267.57 | 227.68 | 85.09 | 65
2 | ALIPURDUAR | Kalchini | Alipurduar Division | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | Constructions of 300 Cum OHR as per Departmental Design & drawing including laying distribution system with new HDPE pipeline (Part-A), RISING MAIN, CONSTRUCTION OF THREE(3) NOS OF BOUNDARY WALL, PATHWAY including soil test, providing FHTC and others allied works for PASCHIM SATALI PWSS Under Alipurduar Division PHE DTE | HQ-A.E | RWS Kalchini Block | ORD/000433/2022-2023 | 2860/ALD | 17/01/2023 | 03/01/2026 | DILIP MAHATO | 497.97 | 365.27 | 73.35 | 74
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Paschim Satali water supply scheme, TW no I, II and III under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000026/2023-2024 | 944/NMD-II | 11/05/2023 | 02/05/2025 | M/S BHOWMIK & CO. | 27.59 | 22.13 | 80.22 | 100
4 | ALIPURDUAR | Kalchini | Alipurduar Division | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | Providing FHTC from existing distribution system as per specification for Paschim Satali PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000261/2023-2024 | 1879/ALD | 07/09/2023 | 03/06/2024 | SATYABRATA BHATTACHERJEE | 7.02 | 0 | 0 | 1
5 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | New Service connection charge for Paschim Satali PWSS P/H No-III |  |  | BILL/00560/2023-2024 | BP-2023-24-186 | 22/06/2023 | 22/06/2023 | WBSEDCL | 1.36 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | New Service connection charge for Paschim Satali PWSS P/H No-I. |  |  | BILL/00558/2023-2024 | BP-2023-24-188 | 22/06/2023 | 22/06/2023 | WBSEDCL | 1.36 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | New Service connection charge for Paschim Satali PWSS P/H No-II |  |  | BILL/00559/2023-2024 | BP-2023-24-187 | 22/06/2023 | 22/06/2023 | WBSEDCL | 1.36 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Alipurduar Division | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | Balance portion of boundary wall and Gap joint of new HDPE/DI pipeline, and land development of HW Site,1st and 2nd site of Paschim Satali PWSS (Part) Kalchini Block Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000474/2023-2024 | 692/ALD | 07/03/2024 | 29/07/2025 | DILIP MAHATO | 61.82 | 0 | 0 | 45
9 | ALIPURDUAR | Kalchini | Alipurduar Division | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | Supply of CIDF/CIPE pipes and specials & Sluice Valve for Paschim Satali Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000479/2023-2024 | 697/ALD | 07/03/2024 | 05/06/2024 | SSPR VALVE MANUFACTURING PVT LTD | 18.08 | 18.08 | 100 | 80
10 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001209/2024-2025 | 823/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
11 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | Yard lighting arrangement at Head Work Site for Different PWSS (NIMTI DOMOHANI and Others) under JJM in the BLOCK: Kalchini, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000170/2025-2026 | 1386/NMD-II | 26/06/2025 | 26/07/2025 | AMUSAR IMPEX PVT LTD | 22.95 | 0 | 0 | 0
12 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
Total | [13 empty] | 1662.17 | 633.16 | 38.09