## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | PRODHANPARA PIPED WATER SUPPLY SCHEME | SM/13247 | New | QUOTATION FOR NSC AT PRADHAN PARA PH NO-I |  |  | BILL/01809/2023-2024 | BP-2023-24-374 | 27/09/2023 | 27/09/2023 | WBSEDCL | 3.96 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | PRODHANPARA PIPED WATER SUPPLY SCHEME | SM/13247 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Pradhan Para water supply scheme, TW no I and II of under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000691/2023-2024 | 2170/NMD-II | 27/07/2023 | 02/12/2024 | SAIKAT SINHA | 18.2 | 17.36 | 95.41 | 100
3 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | PRODHANPARA PIPED WATER SUPPLY SCHEME | SM/13247 | New | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 117/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 8.33 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | PRODHANPARA PIPED WATER SUPPLY SCHEME | SM/13247 | New | Material Requisition To Resource Division |  |  | RTOR000009/2024-2025 | 3614/ALD | 24/10/2024 | 24/10/2024 | Resource Division | 8.11 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | PRODHANPARA PIPED WATER SUPPLY SCHEME | SM/13247 | New | NEW SERVICE CONNECTION CHARGES FOR PRADHAN PARA PWSS P/H NO-II |  |  | BILL/02752/2023-2024 | BP-2023-24-622 | 20/02/2024 | 20/02/2024 | WBSEDCL | 7.75 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | PRODHANPARA PIPED WATER SUPPLY SCHEME | SM/13247 | New | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR, Laying Of Rising Main, Distribution System including soil test and providing FHTC for Prodhanpara PWSS Under Alipurduar Division, PHE Dte. (2nd call) | Alipurduar RWS | JUNIOR ENGINEER | ORD/000512/2022-2023 | 3394/ALD | 16/03/2023 | 01/07/2025 | MESSRS A.B.G CONSTRUCTION | 425.86 | 169.6 | 39.83 | 20
7 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | PRODHANPARA PIPED WATER SUPPLY SCHEME | SM/13247 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
8 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | PRODHANPARA PIPED WATER SUPPLY SCHEME | SM/13247 | New | Solarization of grid connected pumping installation at Different PWSS at Alipurduar-I Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001208/2024-2025 | 822/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | PRODHANPARA PIPED WATER SUPPLY SCHEME | SM/13247 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
Total | [13 empty] | 1301.67 | 186.97 | 14.36