## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Providing balance FHTC for KAYAKHATA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000242/2023-2024 | 1788/ALD | 29/08/2023 | 28/10/2023 | HARI CONSTRUCTION | 11.22 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Supply of CIDF & CISS Pipes and specials for Kayakhata WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000240/2023-2024 | 1775/ALD | 28/08/2023 | 27/09/2023 | HARI CONSTRUCTION | 6.76 | 6.76 | 100 | 100
3 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 3048/ALD | 08/02/2023 | 08/02/2023 | Resource Division | 29.21 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Supply of CIPE Special & CI Jeffy Coupling for Kayakhata Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000480/2023-2024 | 698/ALD | 07/03/2024 | 06/04/2024 | HARI CONSTRUCTION | 15.33 | 15.33 | 100 | 85
5 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 140/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 9.76 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Material Requisition To Resource Division |  |  | RTOR000054/2024-2025 | 4274/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 11.82 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | New Service Connection Charges for Kayakhata PWSS PH NO-II |  |  | BILL/00986/2024-2025 | BP-282/24-25 | 20/08/2024 | 20/08/2024 | WBSEDCL | 9.9 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | NEW SERVICE CONNECTION CHARGE FOR KAYAKHATA PWSS PH NO -I |  |  | BILL/00053/2024-2025 | BP-13/24-25 | 08/04/2024 | 08/04/2024 | WBSEDCL | 3.2 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr. big dia. TW at HW site and 2nd site, LDS with UPVC pipeline, Cons. of 200 cum OHR as per Departmental Design & drawing including soil investigation works, providing FHTC and others allied works for KAYAKHATA PWSS Under Alipurduar Division PHE DTE. (2nd call) | Alipurduar Sadar Sub Division | RWS Alipurduar - I Block,RWS Alipurduar - II Block | ORD/000514/2022-2023 | 3395/ALD | 16/03/2023 | 01/01/2026 | GOUTAM KUMAR DAS | 316.2 | 243.76 | 77.09 | 43
10 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Kayakhata Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/002506/2023-2024 | 2465/NMD-II | 11/08/2023 | 02/03/2025 | KAMAKHYA ENTERPRISE | 20.14 | 12.86 | 63.84 | 85
11 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
12 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Alipurduar-II Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000083/2025-2026 | 1051/ALD | 17/06/2025 | 16/08/2025 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
13 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
14 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Laying of UPVC pipeline at opposite flank of Higher dia in the distribution system and const. of culvert at front of HW site at Kayakhata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - I Block | ORD/000077/2025-2026 | 975/ALD | 12/06/2025 | 10/09/2025 | HARI CONSTRUCTION | 22.06 | 0 | 0 | 0
15 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Solarization of grid connected pumping installation at Different PWSS at Alipurduar -I & II Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000117/2025-2026 | 1293/NMD-II | 12/06/2025 | 10/09/2025 | M/S SAJAHAN CHOWDHURY | 26.61 | 0 | 0 | 0
Total | [13 empty] | 1300.85 | 278.72 | 21.43