## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 | New | Providing balance FHTC for TELIPARA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000216/2023-2024 | 1570/ALD | 23/08/2023 | 22/09/2023 | DHANENDRA SARKAR | 4.32 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 | New | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 222/ALD | 03/05/2023 | 03/05/2023 | Resource Division | 12.68 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 | New | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 2398/ALD | 08/11/2023 | 08/11/2023 | Resource Division | 6.34 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 | New | QUOTATION FOR NEW SERVICE CONNECTION AT TELIPARA PWSS PH NO-I |  |  | BILL/00042/2023-2024 | BP-2023-24-51 | 12/05/2023 | 12/05/2023 | WBSEDCL | 1.21 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 | New | QUOTATION FOR NEW SERVICE CONNECTION AT TELIPARA PWSS PH NO-II |  |  | BILL/00032/2023-2024 | BP-2023-24-50 | 12/05/2023 | 12/05/2023 | WBSEDCL | 1.21 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 | New | Constructions of P/H and T/W Boring by ODEX-165 Method of drilling at HW and 2nd site , LDS with UPVC P/L including rising main and delivery connection, Cons. of 200 Cum OHR as per Departmental Design & drawing along with soil investigation works, providing FHTC and others allied works for TELIPARA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000579/2022-2023 | 3640/ALD | 31/03/2023 | 27/09/2023 | MATRI ENTERPRISE | 225.29 | 167.75 | 74.46 | 85
7 | ALIPURDUAR | Kumargram | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 | New | Material Requisition To Resource Division |  |  | RTOR000048/2024-2025 | 4268/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 13.19 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 | New | Laying of new additional pipeline opposite flanks of the higher dia UPVC pipeline and to connect the scattered house with the distribution system in view of providing FHTC, Construction of RCC pillars for supporting DI Pipe, trial run and others allied works in connection with the Telipara PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000421/2024-2025 | 4907/ALD | 31/01/2025 | 17/03/2025 | MATRI ENTERPRISE | 39.9 | 0 | 0 | 0
10 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 | New | Solarization of grid connected pumping installation at Different PWSS at Kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001206/2024-2025 | 820/NMD-II | 06/03/2025 | 05/04/2025 | WATER TECH | 29.68 | 0 | 0 | 0
11 | ALIPURDUAR | Kumargram | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
12 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
13 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM CHENGMARI and others) under JJM in the BLOCK: Kumargram, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000138/2025-2026 | 1347/NMD-II | 19/06/2025 | 19/07/2025 | S.K ENTERPRISE | 26.74 | 0 | 0 | 0
14 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for TELIPARA water supply scheme, TW no I & II under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000837/2023-2024 | 2421/NMD-II | 10/08/2023 | 04/03/2025 | QUAZI NOZRUL ISLAM | 21.7 | 0 | 0 | 100
15 | ALIPURDUAR | Kumargram | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 | New | Laying of rising main line HDPE PN10, horizontal boring by HDD method, bridge and culvert crossing, construction of pathway, surface drain and chatal, installation of paver block, Land development along with the others allied works at Telipara Headwork site PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000394/2023-2024 | 205/ALD | 16/01/2024 | 10/01/2025 | HARIDAS GHOSH | 31.65 | 0 | 0 | 90
16 | ALIPURDUAR | Kumargram | Alipurduar Division | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 | New | Supply of DI specials and CI Jeffy coupling for Telipara Water Supply Scheme (SM/13303) of Kumargram Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000515/2023-2024 | 834/ALD | 14/03/2024 | 09/03/2025 | HARI CONSTRUCTION | 13.58 | 11.52 | 84.83 | 80
Total | [13 empty] | 1292.01 | 179.27 | 13.88