## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | KALABERIA PIPED WATER SUPPLY SCHEME | SM/13306 | New | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR, Laying Of Rising Main, Distribution System including soil test and providing FHTC for Kolaberia PWSS Under Alipurduar Division, PHE Dte | Alipurduar RWS | JUNIOR ENGINEER,RWS Alipurduar - I Block | ORD/000560/2022-2023 | 3578/ALD | 27/03/2023 | 17/09/2024 | SASANKA ROY | 283.27 | 72.46 | 25.58 | 12
2 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | KALABERIA PIPED WATER SUPPLY SCHEME | SM/13306 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Kalaberia water supply scheme, TW no I and II of under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH,Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000689/2023-2024 | 2163/NMD-II | 27/07/2023 | 01/11/2024 | M/S PARITOSH BHOWMICK & CO. | 18.12 | 0 | 0 | 100
3 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | KALABERIA PIPED WATER SUPPLY SCHEME | SM/13306 | New | Providing FHTC from existing distribution system as per specification for Kalaberia PWSS PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Madarihat - Birpara Block | ORD/000276/2023-2024 | 1890/ALD | 07/09/2023 | 07/10/2023 | SASANKA ROY | 7.46 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | KALABERIA PIPED WATER SUPPLY SCHEME | SM/13306 | New | Material Requisition To Resource Division |  |  | RTOR000094/2023-2024 | 118/ALD | 10/01/2024 |  | Resource Division | 6.56 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | KALABERIA PIPED WATER SUPPLY SCHEME | SM/13306 | New | QUOTATION FOR NSC AT KALABARIA PH NO-I |  |  | BILL/01810/2023-2024 | BP-2023-24-373 | 27/09/2023 |  | WBSEDCL | 4.76 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | KALABERIA PIPED WATER SUPPLY SCHEME | SM/13306 | New | QUOTATION FOR NSC AT KALABARIA PH NO-II |  |  | BILL/01811/2023-2024 | BP-2023-24-372 | 27/09/2023 |  | WBSEDCL | 3.72 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | KALABERIA PIPED WATER SUPPLY SCHEME | SM/13306 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 |  | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | KALABERIA PIPED WATER SUPPLY SCHEME | SM/13306 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 |  | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
Total | [13 empty] | 451.92 | 72.46 | 16.03