## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 | New | Construction of Rig Bored tubewells (1 nos.) by Reverse rotary method of drilling at HW site , construction of pump house and boundary wall at H/W, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Ethelbari Tea Garden PWSS (zone-2) Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000395/2022-2023 | 2660/ALD | 22/12/2022 | 13/08/2024 | M/S DUTTA AND CO | 87.73 | 39.95 | 45.53 | 26
2 | ALIPURDUAR | Falakata | Alipurduar Division | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 | New | Cons. of Rig bored TW(2nos) by Reverse Rotary method of drilling at HW and 2nd site, cons of 200 cum OHR at HW including soil testing, cons. of P/H and B/W at HW,2nd site, Laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for ETHELBARI TG PWSS (ZONE-I)under Birpara Sub-Division, Alipurduar Division, PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000434/2022-2023 | 2861/ALD | 17/01/2023 | 09/10/2026 | DILIP MAHATO | 385.44 | 323.42 | 83.91 | 100
3 | ALIPURDUAR | Falakata | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Ethelbari water supply scheme, TW no I and II of Zone-I under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000677/2023-2024 | 2082/NMD-II | 26/07/2023 | 25/08/2023 | DIAMOND ELECTRICAL WORKS | 20.86 | 19.67 | 94.29 | 100
4 | ALIPURDUAR | Falakata | Alipurduar Division | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 | New | Providing FHTC from existing distribution system as per specification for Ethelbari PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division,RWS Falakata Block | ORD/000260/2023-2024 | 1878/ALD | 07/09/2023 | 20/11/2025 | NARENDRA BHADANI. | 3.87 | 0 | 0 | 100
5 | ALIPURDUAR | Falakata | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Ethelbari water supply scheme, TW no I of Zone-II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/001101/2023-2024 | 2834/NMD-II | 12/10/2023 | 11/11/2023 | MITRA ENTERPRISE | 9.72 | 6.43 | 66.2 | 100
6 | ALIPURDUAR | Falakata | Alipurduar Division | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 | New | Material Requisition To Resource Division |  |  | RTOR000044/2022-2023 | 3486/ALD | 23/03/2023 | 23/03/2023 | Resource Division | 11.43 | 0 | 0 | 0
7 | ALIPURDUAR | Falakata | Alipurduar Division | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 | New | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 2781/ALD | 18/12/2023 | 18/12/2023 | Resource Division | 11.43 | 0 | 0 | 0
8 | ALIPURDUAR | Falakata | Alipurduar Division | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 | New | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 2719/ALD | 13/12/2023 | 13/12/2023 | Resource Division | 60.01 | 0 | 0 | 0
9 | ALIPURDUAR | Falakata | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 | New | QUOTATION FOR NEW SERVICE CONNECTION AT ETHELBARI TG TW NO-II,Z-I |  |  | BILL/00068/2023-2024 | BP-2023-24-63 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.6 | 0 | 0 | 0
10 | ALIPURDUAR | Falakata | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 | New | QUOTATION FOR NEW SERVICE CONNECTION AT ETHELBARI TG TW NO-I,Z-I |  |  | BILL/00069/2023-2024 | BP-2023-24-61 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.6 | 0 | 0 | 0
11 | ALIPURDUAR | Falakata | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 | New | QUOTATION FOR NEW SERVICE CONNECTION AT ETHELBARI TG TW NO-I,Z-II |  |  | BILL/00067/2023-2024 | BP-2023-24-62 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.6 | 0 | 0 | 0
12 | ALIPURDUAR | Falakata | Alipurduar Division | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 | New | Gap filling by HDPE/DI pipe in Ethelbari TG under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000392/2023-2024 | 203/ALD | 16/01/2024 | 01/07/2026 | BHAGWATI BHUJEL | 14.02 | 13.28 | 94.68 | 85
13 | ALIPURDUAR | Falakata | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 | New | Additional Quotation Charges for Ethelbari Zone-II,PH NO-I PWSS |  |  | BILL/00826/2024-2025 | BP-271/24-25 | 12/08/2024 | 12/08/2024 | WBSEDCL | 6.53 | 0 | 0 | 0
14 | ALIPURDUAR | Falakata | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001207/2024-2025 | 821/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
15 | ALIPURDUAR | Falakata | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 | New | Yard lighting arrangement at Head Work Site for Different PWSS (KADAMBINI TG and Others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000137/2025-2026 | 1346/NMD-II | 19/06/2025 | 19/07/2025 | M/S SAJAHAN CHOWDHURY | 23.98 | 0 | 0 | 0
16 | ALIPURDUAR | Falakata | Northern Mechanical Division II | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
Total | [13 empty] | 1394.91 | 402.75 | 28.87