## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Providing FHTC from existing distribution system as per specification for Atiabari TG PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division | ORD/000263/2023-2024 | 1881/ALD | 07/09/2023 | 07/10/2023 | SOUVIK ROY PALADHI | 9.84 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 1271/ALD | 11/08/2023 | 11/08/2023 | Resource Division | 35.15 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 1952/ALD | 12/09/2023 | 12/09/2023 | Resource Division | 129.38 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 2785/ALD | 18/12/2023 | 18/12/2023 | Resource Division | 11.61 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | QUOTATION FOR NSC AT ATIABARI PH NO-II |  |  | BILL/01828/2023-2024 | BP-2023-24-326 | 27/09/2023 | 27/09/2023 | WBSEDCL | 4.7 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new UPVC pipeline , Constructions of 250 Cum OHR as per Departmental Design & drawing including soil investigation works , 2nos pump house & boundary wall, providing FHTC and others allied works for ATIABARI TEA GARDEN PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | Alipurduar Sub Division | ORD/000460/2022-2023 | 2981/ALD | 02/02/2023 | 26/07/2024 | SOUVIK ROY PALADHI | 438.53 | 371.6 | 84.74 | 75
7 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Laying of CIDI Pipes & UPVC pipeline and other allied works for Atiabari Tea Garden PWSS under ALipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division | ORD/000351/2024-2025 | 3421/ALD | 26/09/2024 | 25/11/2024 | SOUVIK ROY PALADHI | 35.9 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Continuation work order for the work of 'Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new UPVC pipeline , Constructions of 250 Cum OHR as per Departmental Design & drawing including soil investigation works , 2nos pump house & boundary wall, providing FHTC and others allied works for ATIABARI TEA GARDEN PWSS Under Alipurduar Division PHE DTE." (As per approval of SE NBC-I P.H.E. Dte. vide e-file no-DPHE-33014/9/2024-EE(ALI_D) SEC-DPHE (Computer No-974282)) | HQ-A.E | Alipurduar Sub Division | ORD/000201/2024-2025 | 1915/ALD | 26/06/2024 | 25/08/2024 | SOUVIK ROY PALADHI | 15.17 | 0 | 0 | 0
9 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Material Requisition To Resource Division |  |  | RTOR000034/2024-2025 | 4250/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 31.17 | 0 | 0 | 0
10 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | New Service Connection for Atiabari T.G PWSS P/H No-I, Kalchini |  |  | BILL/02304/2023-2024 | BP-2023-24-509 | 05/01/2024 | 05/01/2024 | WBSEDCL | 5.81 | 0 | 0 | 0
11 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
12 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Supply of CIDF/CIPE pipes and specials and Sluice Valve for Atiabari TG Water Supply Scheme(SM/14092) of Kalchini Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000521/2023-2024 | 840/ALD | 14/03/2024 | 16/06/2025 | MADHAB SAHA | 16.01 | 0 | 0 | 15
13 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
14 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Yard lighting arrangement at Head Work Site for Different PWSS (NIMTI DOMOHANI and Others) under JJM in the BLOCK: Kalchini, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000170/2025-2026 | 1386/NMD-II | 26/06/2025 | 26/07/2025 | AMUSAR IMPEX PVT LTD | 22.95 | 0 | 0 | 0
15 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
16 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000130/2025-2026 | 1331/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
Total | [13 empty] | 1648.03 | 371.6 | 22.55