## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14093 | New | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 3015/ALD/2022-23 | 07/02/2023 | 07/02/2023 | Resource Division | 13.69 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14093 | New | NEW CONNECTION SETRVICE FOR RAJABHAT T.G. PWSS P/H I,KALCHINI APPLICATION NO 4003210055 |  |  | BILL/01807/2023-2024 | BP-2023-24-379 | 27/09/2023 | 27/09/2023 | WBSEDCL | 4.08 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Alipurduar Division | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14093 | New | Tube well Boring by ODEX-165 Method drilling at HW, First TW Site including laying distribution system with new UPVC PIPELINE, Cons. of 150cum OHR as per departmental Design & drawing , 2nos Pump House & boundary wall, providing FHTC, soil investigation works and others allied works for Rajabhat Tea Garden PWSS Under Alipurduar Division PHE DTE. (2nd call) | HQ-A.E | Alipurduar Sub Division | ORD/000477/2022-2023 | 3194/ALD | 27/02/2023 | 16/02/2025 | ASHIM KUMAR GHOSH | 219.89 | 0 | 0 | 77
4 | ALIPURDUAR | Kalchini | Alipurduar Division | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14093 | New | Providing FHTC from existing distribution system as per specification for Rajabhat TG PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division | ORD/000266/2023-2024 | 1884/ALD | 07/09/2023 | 03/07/2024 | PRITAM DAS | 7.83 | 0 | 0 | 100
5 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14093 | New | New Service Connection for Rajabhat T.G PWSS P/H NO-II,Kalchini |  |  | BILL/02303/2023-2024 | BP-2023-24-504 | 05/01/2024 | 05/01/2024 | WBSEDCL | 3.76 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Alipurduar Division | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14093 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14093 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Raja Bhat TG Water Supply Scheme TWNo-I and II under NMD-II,PHE.Dte,APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001038/2023-2024 | 2679/NMD-II | 11/09/2023 | 10/04/2025 | RMD TRADING | 21.66 | 0 | 0 | 80
8 | ALIPURDUAR | Kalchini | Alipurduar Division | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14093 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
9 | ALIPURDUAR | Kalchini | Alipurduar Division | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14093 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kalchini Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | HQ-A.E | RWS Kalchini Block | ORD/000084/2025-2026 | 1052/ALD | 17/06/2025 | 16/08/2025 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
10 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14093 | New | Yard lighting arrangement at Head Work Site for Different PWSS (NIMTI DOMOHANI and Others) under JJM in the BLOCK: Kalchini, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000170/2025-2026 | 1386/NMD-II | 26/06/2025 | 26/07/2025 | AMUSAR IMPEX PVT LTD | 22.95 | 0 | 0 | 0
11 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14093 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
12 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14093 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000130/2025-2026 | 1331/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
13 | ALIPURDUAR | Kalchini | Alipurduar Division | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14093 | New | Laying of UPVC pipes & other allied works for Rajhabhat TG PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division | ORD/000395/2024-2025 | 4234/ALD | 12/12/2024 | 10/07/2025 | PRITAM DAS | 19.98 | 0 | 0 | 100
Total | [13 empty] | 1223.8 | 0 | 0