## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Providing house connection from Bhatibari Water Supply Scheme (Specially for schools & FHTC) under Alipurduar Division P.H.E. Dte.Part-1 | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000088/2021-2022 | 887/ALD | 03/09/2021 | 03/10/2021 | SREE MAA CONSTRUCTION | 4.87 | 4.87 | 100 | 21
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Providing house connection from Bhatibari Water Supply Scheme (Specially for ICDS & FHTC) under Alipurduar Division P.H.E. Dte.Part-2 | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000089/2021-2022 | 888/ALD | 03/09/2021 | 03/10/2021 | SREE MAA CONSTRUCTION | 4.86 | 4.86 | 100 | 20
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipe at Bhatibari WSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000355/2021-2022 | 2120/ALD | 05/01/2022 | 04/02/2022 | SREE MAA CONSTRUCTION | 4.95 | 4.66 | 94.22 | 0
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Laying distribution pipe with DI and UPVC pipe of Chilurghat, Bhatibari area under Bhatibari Zone-III WSS under Alipurduar Division, PHE Dte.(Part-I) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000387/2022-2023 | 2633/ALD | 21/12/2022 | 19/02/2023 | DAS CONSTRUCTION | 98.5 | 86.88 | 88.2 | 88
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-IV WSS under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000385/2022-2023 | 2631/ALD | 21/12/2022 | 19/02/2023 | DEBAJYOTI SUTRADHAR | 75.53 | 61.22 | 81.06 | 20
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Laying distribution pipe with DI and UPVC pipe of Chilurghat, Kumarijan area under Bhatibari Zone-III WSS under Alipurduar Division, PHE Dte.(Part-II) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000388/2022-2023 | 2634/ALD | 21/12/2022 | 19/02/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 83.66 | 62.39 | 74.57 | 19
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Laying distribution pipe with DI and UPVC pipe of Chikliguri area under Bhatibari Zone-III WSS under Alipurduar Division, PHE Dte.(Part-III) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000389/2022-2023 | 2635/ALD | 21/12/2022 | 19/02/2023 | TAPASH DAS | 74.46 | 43.73 | 58.74 | 21
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Bhatibari PWSS under Alipurduar Division, PHE Dte. Part-8 | Alipurduar Sadar Sub Division | RWS Alipurduar - I Block,RWS Alipurduar - II Block | ORD/000371/2022-2023 | 2615/ALD | 21/12/2022 | 04/02/2023 | GOUTAM KUMAR DAS | 34.6 | 0 | 0 | 0
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Bhatibari PWSS under Alipurduar Division, PHE Dte. Part-9 | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000372/2022-2023 | 2616/ALD | 21/12/2022 | 04/02/2023 | TAPASH KUMAR BHOWMICK | 34.47 | 0 | 0 | 0
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-I WSS under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block,RWS Madarihat - Birpara Block | ORD/000381/2022-2023 | 2627/ALD/ | 21/12/2022 | 19/02/2023 | SHIBA ENTERPRISE | 100.55 | 73.39 | 72.99 | 72
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Providing House Connection (FHTC) at Bhatibari WSS under Alipurduar Division, PHE Dte.Part-5 | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000374/2022-2023 | 2620/ALD | 21/12/2022 | 20/01/2023 | DEBAJYOTI SUTRADHAR | 5.02 | 5.02 | 100 | 22
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Soil investigation work at 4 different places of Bhatibari within Alipurduar District under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000376/2022-2023 | 2622/ALD | 21/12/2022 | 20/01/2023 | R B TESTING | 4.86 | 0 | 0 | 0
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Construction of pathway, surface drain and chatal, land development, along with the other allied works at Bhatibari Zone-IV PWSS under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division |  | ORD/000280/2023-2024 | 1950/ALD | 12/09/2023 | 11/11/2023 | CREATIVE UN EMPLOYED ENGINEERSCO OPER SOCYLIMITED | 13.54 | 0 | 0 | 0
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Construction of pathway, surface drain and chatal, land development, along with the other allied works at Bhatibari Zone-III PWSS under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000273/2023-2024 | 1949/ALD | 12/09/2023 | 11/11/2023 | CREATIVE UN EMPLOYED ENGINEERSCO OPER SOCYLIMITED | 9.75 | 0 | 0 | 0
15 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Construction of pathway, surface drain and chatal, land development, along with the other allied works at Bhatibari Zone-I PWSS under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000279/2023-2024 | 1947/ALD | 12/09/2023 | 11/11/2023 | SAHA ENTERPRISE | 12.4 | 0 | 0 | 0
16 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Balance work of construction of boundary wall of 2nd Site at Bhatibari WSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000251/2021-2022 | 1598/ALD | 22/11/2021 | 06/01/2022 | SREE MAA CONSTRUCTION | 4.79 | 4.77 | 99.59 | 19
17 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Restoration of Laying distribution system by replacing of damaged AC pipeline with UPVC pipeline & constructon of boundary wall, new toilet, repairing of pump house (H/W site) at Bhatibari Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000182/2021-2022 | 1311/ALD | 05/10/2021 | 04/12/2021 | DEBAJYOTI SUTRADHAR | 14.02 | 12 | 85.59 | 21
18 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Providing House Connection (FHTC) at Bhatibari WSS under Alipurduar Division, PHE Dte.Part-4 | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000373/2022-2023 | 2619/ALD | 21/12/2022 | 20/01/2023 | SREE MAA CONSTRUCTION | 5.02 | 4.88 | 97.24 | 21
19 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | QUOTATION |  |  | BILL/02198/2023-2024 | BP-2023-24-475 | 12/12/2023 | 12/12/2023 | WBSEDCL | 4.13 | 0 | 0 | 0
20 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | New service connection for Bhatibari zone-II, P/HNO-I |  |  | BILL/02197/2023-2024 | BP-2023-24-474 | 12/12/2023 | 12/12/2023 | WBSEDCL | 3.91 | 0 | 0 | 0
21 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | QUOTATION |  |  | BILL/02200/2023-2024 | BP-2023-24-477 | 12/12/2023 | 12/12/2023 | WBSEDCL | 8.14 | 0 | 0 | 0
22 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | QUOTATION |  |  | BILL/02201/2023-2024 | BP-2023-24-478 | 12/12/2023 | 12/12/2023 | WBSEDCL | 5.17 | 0 | 0 | 0
23 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | New service connection for Bhatibari PWSS ZONE-III P/HNO-2 |  |  | BILL/02196/2023-2024 | BP-2023-24-473 | 12/12/2023 | 12/12/2023 | WBSEDCL | 5.17 | 0 | 0 | 0
24 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site along with repairing of office godown for Bhatibari Zone-I PWSS Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000390/2022-2023 | 2636/ALD | 21/12/2022 | 19/06/2023 | DULAL DAS | 51.35 | 35.53 | 69.2 | 85
25 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Construction of 1no. Boundary Wall and 2nos. Pump House for BHATIBARI ZONE-III and ZONE-IV PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000391/2022-2023 | 2637/ALD | 21/12/2022 | 10/03/2025 | CREATIVE UN EMPLOYED ENGINEERSCO OPER SOCYLIMITED | 17.67 | 0 | 0 | 100
26 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Bhatibari PWSS under Alipurduar Division, PHE Dte. Part-7 | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000370/2022-2023 | 2614/ALD | 21/12/2022 | 04/02/2023 | HARIDAS GHOSH | 34.76 | 13.04 | 37.5 | 21
27 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Electrification and Earthing of the Newly Renovated pump house No. I and same other allied work ar Bhatibari water supply scheme under JJM. in the Dist. of Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000930/2022-2023 | 652/AMSD | 02/03/2023 | 17/03/2023 | TALUKDAR ENTERPRISE | 0.93 | 0 | 0 | 100
28 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-I WSS under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | RWS Alipurduar - I Block,RWS Alipurduar - II Block | ORD/000383/2022-2023 | 2629/ALD/ | 21/12/2022 | 19/02/2023 | MATRI ENTERPRISE | 100.29 | 92.25 | 91.99 | 87
29 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Construction of 1no. Boundary Wall and 2nos. Tube well Boring by Reverse Rotary Method of drilling for BHATIBARI ZONE-III and ZONE-IV PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000368/2022-2023 | 2612/ALD | 21/12/2022 | 13/06/2024 | AASHIRBAD ENTERPRISE | 24.63 | 23.93 | 97.14 | 100
30 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Construction of concrete platform, pathway and drain along with the repairing of existing boundary wall and drain for effectively stacking the various pipe/ specials items at Alipurduar Sadar Sub-Division Stackyard under the head of augmentation of Bhatibari PWSS under Alipurduar, Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,Birpara Sub Division | ORD/000006/2023-2024 | 03/ALD | 04/04/2023 | 03/07/2023 | HARIDAS GHOSH | 6.38 | 6.02 | 94.36 | 100
31 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | QUOTATION |  |  | BILL/02199/2023-2024 | BP-2023-24-476 | 12/12/2023 | 12/12/2023 | WBSEDCL | 5.51 | 0 | 0 | 0
32 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
33 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-II WSS under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000382/2022-2023 | 2628/ALD/ | 21/12/2022 | 18/05/2023 | TAPASH KUMAR BHOWMICK | 100.89 | 76.17 | 75.5 | 50
34 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-II WSS under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block,RWS Madarihat - Birpara Block | ORD/000384/2022-2023 | 2630/ALD | 21/12/2022 | 09/04/2025 | HARIDAS GHOSH | 98.45 | 80.75 | 82.02 | 18
35 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-IV WSS under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000386/2022-2023 | 2632/ALD | 21/12/2022 | 08/02/2025 | KAMALESH ROY | 74.77 | 65.08 | 87.05 | 87
36 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Laying distribution pipe line by DI pipe (with pillar) along the flank of Alipurduar-Bhatibari PWD Road (From Charmile to Bhatibari) of Bhatibari WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000375/2022-2023 | 2621/ALD | 21/12/2022 | 26/06/2024 | DEBAJYOTI SUTRADHAR | 28.2 | 23.43 | 83.1 | 83
37 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Continuation order of Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.05.2023 to 31.07.2023) | Alipurduar Sadar Sub Division,HQ-A.E | Birpara Sub Division | ORD/000054/2023-2024 | 181/ALD | 27/04/2023 | 27/07/2023 | NIRANJAN KIRTANIA | 0.7 | 0.58 | 83.33 | 0
38 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01/05/2023 to 31/07/2023) | Alipurduar Sadar Sub Division,HQ-A.E | Birpara Sub Division | ORD/000052/2023-2024 | 180/ALD | 27/04/2023 | 27/07/2023 | NIRANJAN KIRTANIA | 0.5 | 0.5 | 100 | 85
39 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Continuation order of Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.08.2023 to 31.10.2023) | Alipurduar Sadar Sub Division,HQ-A.E | Birpara Sub Division | ORD/000253/2023-2024 | 1109/ALD | 28/07/2023 | 28/10/2023 | NIRANJAN KIRTANIA | 0.7 | 0.51 | 72.65 | 0
40 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Construction of pathway, surface drain and chatal, land development, along with the other allied works at Bhatibari Zone-II PWSS under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000271/2023-2024 | 1948/ALD | 12/09/2023 | 11/11/2023 | SWAPAN MALAKAR | 13 | 0 | 0 | 100
41 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01/08/2023 to 31/10/2023) | Alipurduar Sadar Sub Division,HQ-A.E | Birpara Sub Division | ORD/000254/2023-2024 | 1108/ALD | 28/07/2023 | 28/10/2023 | NIRANJAN KIRTANIA | 0.5 | 0.5 | 100 | 0
42 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Bhatibari PWSS under Alipurduar Division, PHE Dte. Part-6 | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000369/2022-2023 | 2613/ALD | 21/12/2022 | 20/07/2023 | TAPASH KUMAR BHOWMICK | 34.47 | 24.13 | 70 | 70
43 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | "Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II P.H.E. Dte." | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001615/2023-2024 | 588/AMSD | 29/12/2023 | 29/02/2024 | MUSTAFI CONCERN | 0.75 | 0 | 0 | 0
44 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Construction of 250cum OHR as per Departmental Design, laying of rising main & delivery connection . Supply of CIDF Specials and others allied works for Bhatibari Z-III PWSS Under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block,RWS Madarihat - Birpara Block | ORD/000196/2024-2025 | 1766/ALD | 07/06/2024 | 01/01/2026 | HARIDAS GHOSH | 103.38 | 37.39 | 36.17 | 50
45 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Construction of 150 cum OHR as per Departmental Design & drawing, laying of rising main & delivery connection . Supply of CIDF Specials and others allied works for Bhatibari Z-II PWSS Under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - I Block | ORD/000423/2024-2025 | 4898/ALD | 30/01/2025 | 29/07/2025 | MATRI ENTERPRISE | 95.67 | 0 | 0 | 0
46 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Construction of 300 cum OHR as per Departmental Design, laying of rising main & delivery connection . Supply of CIDF Specials and others allied works for Bhatibari Z-IPWSS Under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - II Block | ORD/000202/2024-2025 | 1931/ALD | 28/06/2024 | 24/04/2025 | TAPASH KUMAR BHOWMICK | 114.7 | 17.27 | 15.06 | 45
47 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Construction of 150cum OHR as per Departmental Design & drawing, laying of rising main & delivery connection, Supply of CIDF specials and others allied works for Bhatibari Zone -IV PWSS Under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - I Block,RWS Alipurduar - II Block | ORD/000537/2023-2024 | 895/ALD | 15/03/2024 | 03/02/2026 | KAMALESH ROY | 98.47 | 50.36 | 51.14 | 50
48 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Continuation order for "Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II P.H.E. Dte." | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/002126/2023-2024 | 102/AMSD | 21/02/2024 | 21/04/2024 | MUSTAFI CONCERN | 0.75 | 0 | 0 | 0
49 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Continuation order for Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II, PHE Dte. |  |  | ORD/000518/2024-2025 | 340/AMSD | 27/06/2024 | 27/08/2024 | MUSTAFI CONCERN | 0.75 | 0 | 0 | 0
50 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Laying of new UPVC/DI pipeline for filling of left out portion in the distribution system and other allied works in connection with the Augmentation of Bhatibari (Zone-III) PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/14096) | Alipurduar Sadar Sub Division,HQ-A.E | JUNIOR ENGINEER,RWS Alipurduar - II Block | ORD/000222/2024-2025 | 2275/ALD | 05/08/2024 | 31/07/2025 | HARI CONSTRUCTION | 37.43 | 0 | 0 | 65
51 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Constructions of pump house, Boundary wall, laying of UPVC pipeline & Rising main connection for Purba Barachouki area under Bhatibari PWSS proposed Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/14096) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block,RWS Madarihat - Birpara Block | ORD/000224/2024-2025 | 2277/ALD | 05/08/2024 | 31/07/2025 | HARI CONSTRUCTION | 32.72 | 0 | 0 | 35
52 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II, PHE Dte. |  |  | ORD/000005/2024-2025 | 220/AMSD | 26/04/2024 | 26/06/2024 | MUSTAFI CONCERN | 0.75 | 0 | 0 | 0
53 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Continuation order for Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II, PHE Dte. |  |  | ORD/000539/2024-2025 | 476/AMSD | 29/08/2024 | 29/10/2024 | MUSTAFI CONCERN | 0.75 | 0 | 0 | 0
54 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Reparing of Pump House at 3nd site of BHATIBARI PWSS Under Alipurduar Division PHE DTE.(2nd call) |  |  | ORD/000613/2024-2025 | 5603/ALD | 27/03/2025 | 26/05/2025 | SREE MAA CONSTRUCTION | 0.97 | 0 | 0 | 0
55 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector forGround Water Based Piped Water Supply Scheme AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME,Zone-II,P/H No-III and IV under Jal Jeevan Mission NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000058/2025-2026 | 1150/NMD-II | 16/05/2025 | 15/06/2025 | M/S SAJAHAN CHOWDHURY | 22.58 | 0 | 0 | 0
56 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at Bhatibari Zone-II PWSS Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000367/2022-2023 | 2611/ALD/ | 21/12/2022 | 11/09/2024 | RATAN DUTTA | 24.73 | 18.96 | 76.69 | 60
57 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Construction of pump house & sinking of 250 mm x 200 mm x 150mtr Big dia Tubewell at 2nd site of Bhatibari Zone-IV PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block,RWS Madarihat - Birpara Block | ORD/000034/2023-2024 | 365/ALD | 18/05/2023 | 07/01/2025 | MONORAMA ENTERPRISE | 22.01 | 19.1 | 86.79 | 100
58 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for BHATIBARI Water Supply Scheme TWNo- I,II,of Zone-I TWNo- I,II,of Zone-II TWNo- I,II,of Zone-III under NMD-II,PHE.Dte,APD.. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/001098/2023-2024 | 2826/NMD-II | 11/10/2023 | 02/03/2025 | DEY ENTERPRISE (BALLY) | 65.07 | 50.79 | 78.06 | 100
59 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Interconnection of distribution system by laying of DI pipe resting over RCC pillars/hanging support by M.S. Structural works to cross Gadhadhar River and other allied works at Bhatibari PWSS under Alipurduar Division, PHE Dte.(SM/14096) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000358/2024-2025 | 3521/ALD | 04/10/2024 | 02/01/2025 | DEBAJYOTI SUTRADHAR | 5.34 | 1.32 | 24.67 | 100
60 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Constructions of balance portion of Boundary Wall ,path way, Surface drain and chatal, Land development, laying of Rising main line & delivery line connection( for direct supply of water) along with the others allied works at Bhatibari Zone-II PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/14096) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000225/2024-2025 | 2278/ALD | 05/08/2024 | 31/07/2025 | DULAL DAS | 16.03 | 0 | 0 | 100
61 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Sinking of 250mm x 200 mmx 150 mtr big dia Tubewell by Reverse rotary drilling method at Purba barachauki Area for Augmentation of Bhatibari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000381/2024-2025 | 3775/ALD | 13/11/2024 | 12/04/2025 | DAS CONSTRUCTION | 11.48 | 0 | 0 | 100
62 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Repairing of pump house at 4th site of Bhatibari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000445/2024-2025 | 5043/ALD | 17/02/2025 | 17/06/2025 | AN CONSTRUCTION | 1.01 | 0 | 0 | 100
63 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | New Service Connection charges for BHATIBARI Z-II PH NO-III under NMD-II in the District of ALIPURDUAR. |  |  | BILL/02399/2025-2026 |  | 30/10/2025 | 30/10/2025 | WBSEDCL | 7.54 | 0 | 0 | 0
64 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | SM/14096 | Augmentation | Laying of new UPVC/DI pipeline for filling of left out portion in the distribution system and other allied works in connection with the Augmentation of Bhatibari (Zone-I) PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/14096) | Alipurduar Sadar Sub Division | RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Madarihat - Birpara Block | ORD/000254/2024-2025 | 3117/ALD | 30/08/2024 | 11/02/2026 | M/S MAA ELECTRIC ELECTRONIC | 6.45 | 0 | 0 | 70
Total | [13 empty] | 1939.39 | 1006.3 | 51.89