## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 2783/ALD | 18/12/2023 | 18/12/2023 | Resource Division | 9.88 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | QUOTATION FOR NSC AT BHATKHAWA TG TW NO-II |  |  | BILL/01848/2023-2024 | BP-2023-24-391 | 06/10/2023 | 06/10/2023 | WBSEDCL | 7.97 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | QUOTATION FOR NSC AT BHATKHAWA TG PH NO-I |  |  | BILL/01829/2023-2024 | BP-2023-24-325 | 27/09/2023 | 27/09/2023 | WBSEDCL | 12.3 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | QUOTATION FOR NSC AT ATIABARI PH NO-II |  |  | BILL/01830/2023-2024 |  | 25/09/2023 | 25/09/2023 | WBSEDCL | 7.97 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new HDPE pipeline , Constructions of 150 Cum OHR as per Departmental Design & drawing , TWO nos pump house & boundary wall, providing FHTC, Soil Investigation work and other allied works for BHATKHAWA TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | Alipurduar Sub Division | ORD/000475/2022-2023 | 3193/ALD | 27/02/2023 | 31/12/2024 | S.G. CONSTRUCTION | 325.36 | 109.18 | 33.56 | 60
6 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | Providing FHTC from existing distribution system as per specification for Bhatkhawa TG PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division | ORD/000265/2023-2024 | 1883/ALD | 07/09/2023 | 04/05/2024 | PRANAB GHOSH | 7.16 | 0 | 0 | 100
7 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | Material Requisition To Resource Division |  |  | RTOR000033/2024-2025 | 4249/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 29.54 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
9 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bhatkhawa TG water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000704/2023-2024 | 2147/NMD-II | 27/07/2023 | 26/08/2023 | MUSTAFI CONCERN | 18.76 | 0 | 0 | 45
10 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001209/2024-2025 | 823/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
11 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | Supply and installation of scheme information board at different PWSS site of Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Madarihat - Birpara Block | ORD/000112/2025-2026 | 1394/ALD | 16/07/2025 | 14/09/2025 | M/S SARKAR & CO | 3.64 | 0 | 0 | 0
12 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
13 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | Expenditure for different PWSS land registration and subsequent mutation process as compliance for PHED and Land commissioner authorise to overcome the stalemate and initiation of due diligence process in Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kumargram Block | ORD/000113/2025-2026 | 1395/ALD | 16/07/2025 | 30/08/2025 | M/S SARKAR & CO | 2 | 0 | 0 | 0
14 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | Laying of HDPE (PN-6) bring crossing work including land development and allied work at Bhatkhawa Tea Garden Piped Water Supply Scheme Alipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division | ORD/000181/2025-2026 | 1884/ALD | 27/08/2025 | 25/11/2025 | PRITAM DAS | 21.91 | 0 | 0 | 0
Total | [13 empty] | 1265.59 | 109.18 | 8.63