## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME | SM/14216 | New | Construction of Tubewell by ODEX-165 method of drilling at HW site, construction of pump house and boundary wall at H/W site, laying of distribution line and providing FHTC as per Departmental Design & drawing for Garochera Bandapani PWSS Under Birpara Sub-division, Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000451/2022-2023 | 2922/ALD | 19/01/2023 | 19/05/2023 | RATAN DUTTA | 73.26 | 35.62 | 48.62 | 62
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME | SM/14216 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Garochira Bandapani Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000400/2023-2024 | 1674/NMD-II | 17/07/2023 | 16/08/2023 | PRAGATI CONSTRUCTION COMPANY | 9.38 | 0 | 0 | 100
3 | ALIPURDUAR | Madarihat | Alipurduar Division | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME | SM/14216 | New | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 1953/ALD | 12/09/2023 |  | Resource Division | 33.29 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME | SM/14216 | New | QUOTATION FOR NEW SERVICE CONNECTION AT GAROCHIRA BANDAPANI TW NO-I |  |  | BILL/00064/2023-2024 | BP-2023-24-58 | 13/05/2023 |  | WBSEDCL | 1.46 | 0 | 0 | 0
Total | [13 empty] | 117.4 | 35.62 | 30.34