## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | NURPUR PIPED WATER SUPPLY SCHEME. | SM/14218 | New | Cons. Of pump house & TW boring by ODEX-165 method of drilling at HW & 2nd site, LDS with UPVC pipeline including rising main & delivery connection, cons. Of 100cum OHR as per departmental design & drawing along with soil investigation works, providing FHTC including platform and others allied works for NURPUR PWSS Under Alipurduar Division PHE DTE. (2nd call) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000478/2022-2023 | 3195/ALD | 27/02/2023 | 17/02/2025 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 182.4 | 141.29 | 77.46 | 95
2 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | NURPUR PIPED WATER SUPPLY SCHEME. | SM/14218 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Nurpur Water Supply Scheme TW No.- I ,II and III under NMD-II,PHE.Dte,APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000035/2023-2024 | 983/NMD-II | 15/05/2023 | 14/06/2023 | RMD TRADING | 28.75 | 21.63 | 75.23 | 100
3 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | NURPUR PIPED WATER SUPPLY SCHEME. | SM/14218 | New | Gap filling of distribution line with DI/CI/UPVC pipe at Nurpur WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000192/2023-2024 | 1468/ALD | 16/08/2023 | 15/10/2023 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 20.69 | 17.31 | 83.7 | 70
4 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | NURPUR PIPED WATER SUPPLY SCHEME. | SM/14218 | New | Supply of CIDF & CISS Pipes and specials for NURPUR WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000237/2023-2024 | 1591/ALD | 25/08/2023 | 24/09/2023 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 6.76 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | NURPUR PIPED WATER SUPPLY SCHEME. | SM/14218 | New | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 1258/ALD | 10/08/2023 | 10/08/2023 | Resource Division | 13.15 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | NURPUR PIPED WATER SUPPLY SCHEME. | SM/14218 | New | Quotation for NSC at P/H No.I under Nurpur W/S/S |  |  | BILL/00597/2023-2024 | BP-2023-24-175 | 15/06/2023 | 15/06/2023 | WBSEDCL | 1.31 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | NURPUR PIPED WATER SUPPLY SCHEME. | SM/14218 | New | Quotation for NSC at P/H No.II under Nurpur W/S/S |  |  | BILL/00598/2023-2024 | BP-2023-24-176 | 15/06/2023 | 15/06/2023 | WBSEDCL | 1.31 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | NURPUR PIPED WATER SUPPLY SCHEME. | SM/14218 | New | Laying of rising main line with HDPE PN10, horizontal boring by HDD method , bridge and culvert crossing, construction of pathway, surface drain and chatal, installation of paver block, land development along with the other allied works at NURPUR HW site PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000368/2023-2024 | 84/ALD | 10/01/2024 | 09/04/2024 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 33.28 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | NURPUR PIPED WATER SUPPLY SCHEME. | SM/14218 | New | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte. (from 01.01.2024 to 31.12.2024) | Alipurduar Sadar Sub Division,HQ-A.E | Birpara Sub Division | ORD/000498/2023-2024 | 487/ALD | 15/02/2024 | 15/02/2025 | MATRI ENTERPRISE | 4.8 | 0 | 0 | 0
10 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | NURPUR PIPED WATER SUPPLY SCHEME. | SM/14218 | New | New Service Connection Charges for Nurpur, Uttar Rampur, PWSS PH NO-3 |  |  | BILL/00824/2024-2025 | BP-292/24-25 | 20/08/2024 | 20/08/2024 | WBSEDCL | 13.73 | 0 | 0 | 0
11 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | NURPUR PIPED WATER SUPPLY SCHEME. | SM/14218 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
12 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | NURPUR PIPED WATER SUPPLY SCHEME. | SM/14218 | New | Solarization of grid connected pumping installation at Different PWSS at Alipurduar -I & II Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000117/2025-2026 | 1293/NMD-II | 12/06/2025 | 10/09/2025 | M/S SAJAHAN CHOWDHURY | 26.61 | 0 | 0 | 0
13 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | NURPUR PIPED WATER SUPPLY SCHEME. | SM/14218 | New | Additional Quotation for Nurpur P/H No.III |  |  | BILL/02165/2024-2025 | BP-468/24-25 | 21/01/2025 | 21/01/2025 | WBSEDCL | 2.1 | 0 | 0 | 0
Total | [13 empty] | 1061.02 | 180.23 | 16.99