## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 3046/ALD | 08/02/2023 | 08/02/2023 | Resource Division | 25.4 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 2397/ALD | 08/11/2023 | 08/11/2023 | Resource Division | 6.18 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | NEW SEVICE CONNECTION CHARGES FOR TURTURI PWSS P/H NO.I |  |  | BILL/00739/2023-2024 | BP-2023-24-282 | 18/08/2023 | 18/08/2023 | WBSEDCL | 1.48 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | NEW SEVICE CONNECTION CHARGES FOR TURTURI PWSS P/H NO.II |  |  | BILL/00740/2023-2024 | BP-2023-24-273 | 18/08/2023 | 18/08/2023 | WBSEDCL | 1.48 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | Tube well boring by ODEX-165 Method of drilling, Construction of Pump House, Boundary wall at proposed 3rd site of Turturi under Alipurduar Division, PHE Dte | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000323/2023-2024 | 2420/ALD | 09/11/2023 | 13/01/2025 | TAPASH KUMAR BHOWMICK | 17.4 | 0 | 0 | 70
6 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | Laying of HDPE/DI Pipeline, horizontal boring by HDD method, bridge and culvert crossing, providing FHTC, specials repair with trial run of pipeline and allied works at Chuniajhora PWSS under Alipurduar Division, PHE Dte.(SM/14219 & SM/10179) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000460/2023-2024 | 672/ALD | 06/03/2024 | 01/11/2024 | ASHOK SAPKOTA | 19.39 | 0 | 0 | 100
7 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | Supply of CIDF Specials & Jeffy Coupling for Turturi (SM/14219) WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000403/2024-2025 | 4539/ALD | 26/12/2024 | 25/01/2025 | SOUVIK ROY PALADHI | 19.99 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | Supply of CIDF & CISS Pipes and specials for Turturi Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000219/2023-2024 | 1579/ALD | 24/08/2023 | 23/09/2023 | TAPASH KUMAR BHOWMICK | 11.27 | 0 | 0 | 85
9 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | Continuation for the work of Collection of house hold details at prescribed format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same (soft copy) to P.H.E. Dte. Part-B | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000255/2023-2024 | 1107/ALD | 28/07/2023 | 25/11/2023 | TAPASH KUMAR BHOWMICK | 4.67 | 0 | 0 | 100
10 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | Material Requisition To Resource Division |  |  | RTOR000015/2024-2025 | 3949/ALD | 26/11/2024 | 26/11/2024 | Resource Division | 6.18 | 0 | 0 | 0
11 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | Material Requisition To Resource Division |  |  | RTOR000056/2024-2025 | 4276/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 7.63 | 0 | 0 | 0
12 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | ADDITIONAL QUOTATION FOR TURTURI PH NO-II |  |  | BILL/02959/2023-2024 | BP-02/24-25 | 08/04/2024 | 08/04/2024 | WBSEDCL | 7.36 | 0 | 0 | 0
13 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | ADDITIONAL QUOTATION FOR INFRASTRUCTURE DEVELOPMENT FOR TURTURI P/H NO-I |  |  | BILL/00047/2024-2025 | BP-03/24-25 | 08/04/2024 | 08/04/2024 | WBSEDCL | 4.54 | 0 | 0 | 0
14 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | Cons. of Pump House & Tube well Boring by ODEX-165 Method drilling at HW Site & 2nd Site, laying distribution system with UPVC pipeline including rising main & delivery connection, Cons. of 150cum OHR as per departmental Design & drawing along with soil investigation works, providing FHTC including cons. of platform and others allied works for TURTURI PWSS Under Alipurduar Division, PHE DTE | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000551/2022-2023 | 3574/ALD | 27/03/2023 | 16/03/2025 | TAPASH KUMAR BHOWMICK | 399.05 | 0 | 0 | 90
15 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | Providing balance FHTC for TURTURI PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000217/2023-2024 | 1571/ALD | 23/08/2023 | 31/12/2024 | TAPASH KUMAR BHOWMICK | 6.81 | 0 | 0 | 0
16 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
17 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Alipurduar-II Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000083/2025-2026 | 1051/ALD | 17/06/2025 | 16/08/2025 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
18 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
19 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | Solarization of grid connected pumping installation at different PWSS at Alipurduar -II block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001205/2024-2025 | 819/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
20 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Turturi water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000785/2023-2024 | 2339/NMD-II | 01/08/2023 | 02/12/2024 | M/S J.K ENGINEERING CO. | 18.77 | 0 | 0 | 80
Total | [13 empty] | 1405.18 | 0 | 0