## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | TORSHA FOREST PIPED WATER SUPPLY SCHEME | SM/14220 | New | QUOTATION FOR NSC AT TORSHA FOREST PH NO-I |  |  | BILL/01812/2023-2024 | BP-2023-24-375 | 27/09/2023 | 27/09/2023 | WBSEDCL | 4.07 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | TORSHA FOREST PIPED WATER SUPPLY SCHEME | SM/14220 | New | Boring of Tubewell, Construction of pump house, boundary wall, Laying of Rising main, distribution system and providing FHTC for Torsha Forest PWSS under Alipurduar Division PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000448/2022-2023 | 2919/ALD | 19/01/2023 | 10/09/2024 | KAMALESH ROY | 79.66 | 71.83 | 90.18 | 94
3 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | TORSHA FOREST PIPED WATER SUPPLY SCHEME | SM/14220 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Torsha Forest Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000045/2023-2024 | 1060/NMD-II | 26/05/2023 | 25/06/2023 | DIPA CHHETRI | 9.38 | 9.25 | 98.52 | 100
4 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | TORSHA FOREST PIPED WATER SUPPLY SCHEME | SM/14220 | New | Laying of remaining Distribution Line and providing FHTC at different areas under Torsha FOREST PWSS under Alipurduar Division, PHE Dte | Alipurduar RWS | JUNIOR ENGINEER | ORD/000221/2023-2024 | 1581/ALD | 24/08/2023 | 23/10/2023 | KAMALESH ROY | 10.84 | 10.84 | 100 | 100
5 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | TORSHA FOREST PIPED WATER SUPPLY SCHEME | SM/14220 | New | Solarization of grid connected pumping installation at Different PWSS at Alipurduar-I Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001208/2024-2025 | 822/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | TORSHA FOREST PIPED WATER SUPPLY SCHEME | SM/14220 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
Total | [13 empty] | 859.04 | 91.92 | 10.7