## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 | New | Providing FHTC from existing distribution system as per specification for Uttar Rangalibazna PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000304/2023-2024 | 2135/ALD | 03/10/2023 | 02/11/2023 | MANI PRADHAN | 1.08 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Alipurduar Division | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 | New | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 2701/ALD | 12/12/2023 | 12/12/2023 | Resource Division | 84.45 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 | New | NEW CONNECTION SERVICE FOR UTTAR RANGALIBAZNA PWSS P/H NO II |  |  | BILL/01796/2023-2024 | BP-2023-24-363 | 27/09/2023 | 27/09/2023 | WBSEDCL | 5.74 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 | New | NEW CONNECTION SETRVICE FOR UTTAR RANGALIBAZNA PWSS P/H NO I APPLICATION NO 4003065172 |  |  | BILL/01793/2023-2024 | BP-2023-24-362 | 27/09/2023 | 27/09/2023 | WBSEDCL | 7.7 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Alipurduar Division | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 | New | Cons. of Rig bored TW(2nos) by ODEX-165 method of drilling at HW and 2nd site, cons of 100 cum OHR at HW including soil testing, cons. of P/H and B/W at HW,2nd site, Laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing , providing FHTC and others allied works for Uttar Rangalibazna PWSS under Birpara Sub-Division, Alipurduar Division, PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000546/2022-2023 | 3570/ALD | 27/03/2023 | 30/09/2025 | SAMIRON PODDER | 271.9 | 112.72 | 41.46 | 11
6 | ALIPURDUAR | Madarihat | Alipurduar Division | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 | New | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 114/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 4.49 | 0 | 0 | 0
7 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000133/2025-2026 | 1334/NMD-II | 18/06/2025 | 16/09/2025 | M. M. ENTERPRISE | 16.38 | 0 | 0 | 0
8 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
9 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for UTTAR RANGALIBAZNA water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000685/2023-2024 | 2139/NMD-II | 27/07/2023 | 02/04/2025 | DILIP MAHATO | 18.33 | 4.47 | 24.4 | 100
Total | [13 empty] | 1136.23 | 117.2 | 10.31