## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Cons of PH and Sinking of 250 mm x 200 mm X 150 mtr Big dia TW at HW site , 2nd site and 3rd TW site LDS with UPVC p/line , cons of 100 Cum OHR incl the Soil investigation works providing FHTC and others allied works for Pakriguri PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000576/2022-2023 | 3637/ALD | 31/03/2023 | 21/09/2024 | DEBAJYOTI SUTRADHAR | 183.6 | 0 | 0 | 65
2 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Pakriguri water supply scheme, TW no I,II and III under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000835/2023-2024 | 2415/NMD-II | 10/08/2023 | 09/09/2023 | ALPHA ENTERPRISE | 27.58 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Providing balance FHTC for PAKRIGURI PWSSunder Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000212/2023-2024 | 1566/ALD | 23/08/2023 | 22/09/2023 | SREE MAA CONSTRUCTION | 3.43 | 0 | 0 | 15
4 | ALIPURDUAR | Kumargram | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Supply of CIDF Specials & Jeffy Coupling for Pakriguri (SM/14223) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000399/2024-2025 | 4265/ALD | 13/12/2024 | 12/01/2025 | BARMAN ENTERPRISE | 19.64 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 221/ALD | 03/05/2023 |  | Resource Division | 9.77 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 122/ALD | 10/01/2024 |  | Resource Division | 3.71 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Material Requisition To Resource Division |  |  | RTOR000029/2024-2025 | 3987/ALD | 27/11/2024 |  | Resource Division | 3.71 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Material Requisition To Resource Division |  |  | RTOR000049/2024-2025 | 4269/ALD | 13/12/2024 |  | Resource Division | 25.24 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PAKRIGURI PWSS PH NO-II |  |  | BILL/00040/2023-2024 | BP-2023-24-46 | 12/05/2023 |  | WBSEDCL | 1.21 | 0 | 0 | 0
10 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PAKRIGURI PWSS PH NO-I |  |  | BILL/00039/2023-2024 | BP-2023-24-47 | 12/05/2023 |  | WBSEDCL | 1.21 | 0 | 0 | 0
11 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PAKRIGURI PWSS PH NO-III |  |  | BILL/00041/2023-2024 | BP-2023-24-45 | 12/05/2023 |  | WBSEDCL | 1.21 | 0 | 0 | 0
12 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Additional quotation for Pakriguri PH NO-1 |  |  | BILL/00864/2024-2025 | BP-263/24-25 | 09/08/2024 |  | WBSEDCL | 3.01 | 0 | 0 | null
13 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Additional quotation for Pakriguri PH NO-1 |  |  | BILL/00864/2024-2025 | BP-263/24-25 | 09/08/2024 |  | WBSEDCL | 3.01 | 0 | 0 | null
14 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Additional quotation for PAKRIGURI PH NO-3 |  |  | BILL/00862/2024-2025 | BP-264/24-25 | 09/08/2024 |  | WBSEDCL | 5.46 | 0 | 0 | null
15 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Additional quotation for PAKRIGURI PH NO-3 |  |  | BILL/00862/2024-2025 | BP-264/24-25 | 09/08/2024 |  | WBSEDCL | 5.46 | 0 | 0 | null
16 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Additional quotation for PAKRIGURI PH NO-2 |  |  | BILL/00863/2024-2025 | BP-262/24-25 | 09/08/2024 |  | WBSEDCL | 5.41 | 0 | 0 | null
17 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Additional quotation for PAKRIGURI PH NO-2 |  |  | BILL/00863/2024-2025 | BP-262/24-25 | 09/08/2024 |  | WBSEDCL | 5.41 | 0 | 0 | null
Total | [13 empty] | 308.08 | 0 | 0