## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 221/ALD | 03/05/2023 | 03/05/2023 | Resource Division | 9.77 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PAKRIGURI PWSS PH NO-II |  |  | BILL/00040/2023-2024 | BP-2023-24-46 | 12/05/2023 | 12/05/2023 | WBSEDCL | 1.21 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PAKRIGURI PWSS PH NO-III |  |  | BILL/00041/2023-2024 | BP-2023-24-45 | 12/05/2023 | 12/05/2023 | WBSEDCL | 1.21 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PAKRIGURI PWSS PH NO-I |  |  | BILL/00039/2023-2024 | BP-2023-24-47 | 12/05/2023 | 12/05/2023 | WBSEDCL | 1.21 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Providing balance FHTC for PAKRIGURI PWSSunder Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000212/2023-2024 | 1566/ALD | 23/08/2023 | 22/09/2023 | SREE MAA CONSTRUCTION | 3.43 | 0 | 0 | 15
6 | ALIPURDUAR | Kumargram | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 122/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 3.71 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Material Requisition To Resource Division |  |  | RTOR000029/2024-2025 | 3987/ALD | 27/11/2024 | 27/11/2024 | Resource Division | 3.71 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Material Requisition To Resource Division |  |  | RTOR000049/2024-2025 | 4269/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 25.24 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Additional quotation for Pakriguri PH NO-1 |  |  | BILL/00864/2024-2025 | BP-263/24-25 | 09/08/2024 | 09/08/2024 | WBSEDCL | 3.01 | 0 | 0 | 0
10 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Additional quotation for PAKRIGURI PH NO-3 |  |  | BILL/00862/2024-2025 | BP-264/24-25 | 09/08/2024 | 09/08/2024 | WBSEDCL | 5.46 | 0 | 0 | 0
11 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Additional quotation for PAKRIGURI PH NO-2 |  |  | BILL/00863/2024-2025 | BP-262/24-25 | 09/08/2024 | 09/08/2024 | WBSEDCL | 5.41 | 0 | 0 | 0
12 | ALIPURDUAR | Kumargram | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Cons of PH and Sinking of 250 mm x 200 mm X 150 mtr Big dia TW at HW site , 2nd site and 3rd TW site LDS with UPVC p/line , cons of 100 Cum OHR incl the Soil investigation works providing FHTC and others allied works for Pakriguri PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000576/2022-2023 | 3637/ALD | 31/03/2023 | 15/03/2026 | DEBAJYOTI SUTRADHAR | 183.6 | 136.16 | 74.16 | 65
13 | ALIPURDUAR | Kumargram | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Supply of CIDF Specials & Jeffy Coupling for Pakriguri (SM/14223) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000399/2024-2025 | 4265/ALD | 13/12/2024 | 11/02/2025 | BARMAN ENTERPRISE | 19.64 | 3.38 | 17.21 | 51
14 | ALIPURDUAR | Kumargram | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Construction of pumphouse & boundary wall for 3rd site, laying of distribution system with UPVC and DI pipeline, providing FHTC, Rising main and other allied works for Pakriguri PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000422/2024-2025 | 4906/ALD | 31/01/2025 | 01/05/2025 | DEBAJYOTI SUTRADHAR | 23.9 | 0 | 0 | 0
15 | ALIPURDUAR | Kumargram | Alipurduar Division | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
16 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
17 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini, Madarihat -Birpara ,kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000131/2025-2026 | 1332/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
18 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM CHENGMARI and others) under JJM in the BLOCK: Kumargram, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000138/2025-2026 | 1347/NMD-II | 19/06/2025 | 19/07/2025 | S.K ENTERPRISE | 26.74 | 0 | 0 | 0
19 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Pakriguri water supply scheme, TW no I,II and III under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000835/2023-2024 | 2415/NMD-II | 10/08/2023 | 02/05/2025 | ALPHA ENTERPRISE | 27.58 | 0 | 0 | 100
Total | [13 empty] | 1172.64 | 139.54 | 11.9