## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Laying of HDPE pipe line for the Birpara Water Supply Scheme under Alipurduar Division,PHE Dte.(Part-3) | Birpara A.E | Birpara Sub Division | ORD/000231/2021-2022 | 1570/ALD | 22/11/2021 | 16/01/2023 | SOUVIK ROY PALADHI | 37.07 | 29.87 | 80.58 | 61
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Laying of HDPE pipe line for the Birpara Water Supply Scheme under Alipurduar Division,PHE Dte.(Part-2) | Birpara A.E | Birpara Sub Division | ORD/000230/2021-2022 | 1571/ALD | 22/11/2021 | 21/01/2022 | PRAMESH LAMA | 51.34 | 44.47 | 86.62 | 7
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) | Birpara A.E | Birpara Sub Division | ORD/000320/2020-2021 | 1453/ALD | 25/01/2021 | 11/03/2021 | PRAMESH LAMA | 33.97 | 0 | 0 | 100
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Laying of CI/DI/MS/HDPE pipe and providing FHTC for BIRPARA TEA GARDEN (ZONE-3) AREA PWSS Under Alipurduar Division PHE DTE. PART-A | Birpara A.E | Alipurduar Sub Division | ORD/000441/2022-2023 | 2870/ALD | 17/01/2023 | 18/03/2023 | ANUP KUNDU CONSTRUCTION CO. | 95.98 | 81.06 | 84.46 | 7
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for BirparaZone-I (North) PWSS under Alipurduar Division, PHE Dte. Part-1 | Alipurduar RWS,Birpara A.E | Birpara Sub Division | ORD/000444/2022-2023 | 2873/ALD | 17/01/2023 | 23/06/2025 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 24.27 | 2.95 | 12.14 | 58
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Birpara (South) PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000447/2022-2023 | 2876/ALD | 17/01/2023 | 03/03/2023 | DILIP MAHATO | 34.6 | 0 | 0 | 0
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Laying of CI/DI/MS/HDPE pipe and providing FHTC for BIRPARA TEA GARDEN (ZONE-2) AREA PWSS Under Alipurduar Division PHE DTE. PART-A | Birpara A.E | Alipurduar Sub Division | ORD/000440/2022-2023 | 2869/ALD | 17/01/2023 | 18/03/2023 | AMBITIOUS ENTERPRISE | 97.44 | 41.77 | 42.87 | 7
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Birpara Zone-II (Middle) PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000446/2022-2023 | 2875/ALD | 17/01/2023 | 03/03/2023 | NARENDRA BHADANI. | 24.11 | 0 | 0 | 0
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of 550cum. OHR for Birpara TG (Middle) Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000438/2022-2023 | 2867/ALD | 17/01/2023 | 16/07/2023 | DILIP MAHATO | 98.12 | 86.15 | 87.79 | 85
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Laying of CI/DI/MS/HDPE pipe and providing FHTC for BIRPARA TEA GARDEN (ZONE-3) AREA PWSS Under Alipurduar Division PHE DTE. PART-C | Birpara A.E | Birpara Sub Division | ORD/000443/2022-2023 | 2872/ALD | 17/01/2023 | 18/03/2023 | DILIP MAHATO | 96.76 | 74.45 | 76.94 | 65
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of pump house boundary wall Tubewell boring (by ODEX-165 method of drilling) and rising main for Zone-III 3rd TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000014/2023-2024 | 166/ALD | 26/04/2023 | 18/08/2024 | RATAN DUTTA | 31.78 | 18.23 | 57.36 | 65
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of pump house boundary wall Tubewell boring (by ODEX-165 method of drilling) and rising main for Zone-II 3rd TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000009/2023-2024 | 93/ALD | 18/04/2023 | 16/08/2023 | SUBHAK CHIK BARAIK | 31.63 | 9.71 | 30.71 | 100
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of pump house, Boundary Wall, Tube well Boring (by ODEX-165 method of drilling) and Rising main for Zone-I 1st TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000040/2023-2024 | 386/ALD | 19/05/2023 | 16/09/2023 | KAJAL KUMAR DE | 32.74 | 20.26 | 61.89 | 30
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of pump house, Boundary Wall, Tube well Boring (by ODEX-165 method of drilling) and Rising main for Zone-III 2nd TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000171/2023-2024 | 962/ALD | 12/07/2023 | 09/11/2023 | SUBIR GHOSH | 32.45 | 0 | 0 | 0
15 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of pump house, Boundary Wall, Tube well Boring (by ODEX-165 method of drilling) and Rising main for Zone-II 1st TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000158/2023-2024 | 663/ALD | 07/06/2023 | 29/09/2024 | BRAJA GOPAL SAHA | 31.58 | 22.36 | 70.79 | 20
16 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Providing FHTC from existing distribution system as per specification for BIRPARA PWSS under Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000296/2023-2024 | 2105/ALD | 29/09/2023 | 28/11/2023 | GIRIRAJ ENTERPRISE | 34.39 | 0 | 0 | 0
17 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro mechanical component along with Cu. wound line voltage corrector for Augmentation of Birpara water supply scheme TW No.- I,II and III of Zone-I and TW No.- I,II,III and IV of Zone-II and TW No.- I,II and III of Zone-III under Northern Mechanical Division-II, PHE Dte, Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001136/2023-2024 | 2873/NMD-II | 17/10/2023 | 02/01/2026 | EASTERN INDIA SALES & SERVICE | 176.42 | 118.2 | 67 | 80
18 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Birpara Zone-I (North) PWSS under Alipurduar Division, PHE Dte. Part-2 | Alipurduar RWS |  | ORD/000445/2022-2023 | 2874/ALD | 17/01/2023 | 03/03/2023 | BILTU DAS | 24.22 | 0 | 0 | 0
19 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of Pump House, B/wall, TW boring by ODEX-165 method of drilling and rising main for Zone-I Headwork TW Site at Augmentation od Birpara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000342/2023-2024 | 2543/ALD | 28/11/2023 | 20/07/2025 | KAMALESH ROY | 44.55 | 5.69 | 12.77 | 50
20 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of Pump House, B/wall, TW boring by ODEX-165 method of drilling and rising main for Zone-I 3rd TW Site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000350/2023-2024 | 2602/ALD | 04/12/2023 | 30/03/2025 | FAUDA SINGH CHHETRI | 31.46 | 18.97 | 60.31 | 61
21 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | "Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II P.H.E. Dte." | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001249/2023-2024 | 419/AMSD | 16/10/2023 | 16/12/2023 | MUSTAFI CONCERN | 0.69 | 0 | 0 | 100
22 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of Pump House, B/wall, TW boring by ODEX-165 method of drilling and rising main for Zone-III Headwork TW Site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000343/2023-2024 | 2544/ALD | 28/11/2023 | 27/03/2026 | RATAN DUTTA | 46.23 | 6.37 | 13.78 | 5
23 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Tube well Boring by ODEX-165 Method of drilling at TUBE WELL site including laying distribution system with new HDPE pipeline ,One nos pump house & boundary wall, providing FHTC and others allied works for Bhutri Forest PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000010/2023-2024 | 94/ALD | 18/04/2023 | 16/08/2023 | FAUDA SINGH CHHETRI | 34.7 | 29.27 | 84.36 | 100
24 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Supply of drinking water through tanker by hired vehicle to mitigate drinking water crisis at Huntapara TG, Dhumchipara TG and Gargenda TG and lankapara TG under Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000309/2023-2024 | 2174/ALD | 06/10/2023 | 20/11/2023 | BHAGWATI BHUJEL | 9.82 | 9.82 | 100 | 100
25 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 2722/ALD | 13/12/2023 | 13/12/2023 | Resource Division | 137.01 | 0 | 0 | 0
26 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW CONNECTION FOR BIRPARA(AUG) ZONE- IPHNO-II |  |  | BILL/02001/2023-2024 | BP-2023-24-460 | 07/12/2023 | 07/12/2023 | WBSEDCL | 4.26 | 0 | 0 | 0
27 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW CONNECTION FOR BIRPARA (AUG) ZONE-I PHNO-III |  |  | BILL/02002/2023-2024 | BP-2023-24-461 | 07/12/2023 | 07/12/2023 | WBSEDCL | 5.5 | 0 | 0 | 0
28 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | QUOTATION FOR BURNT METER AT BIRPARA |  |  | BILL/01825/2023-2024 | BP-2023-24-329 | 27/09/2023 | 27/09/2023 | WBSEDCL | 0.09 | 0 | 0 | 0
29 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | SHIFTING OF LTOH LINE AT BHANUNAGAR UNDER BIRPARA CCC |  |  | BILL/00234/2023-2024 | BP-2023-24-130 | 23/05/2023 | 23/05/2023 | WBSEDCL | 0.47 | 0 | 0 | 0
30 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | SOIL INVESTIGATION AT OHR AND CONS. OF 450 CUM OHR AT ZONE-3 FOR AUGMENTATIN OF BIRPARA PWSS UNDER ALIPURDUAR DIVISION OF NORTH BENGAL CIRCLE-I, PHE DTE. | Birpara A.E | Birpara Sub Division,RWS Falakata Block | ORD/000433/2023-2024 | 234/ALD | 17/01/2024 | 01/02/2025 | AMBITIOUS ENTERPRISE | 239.31 | 25.15 | 10.51 | 55
31 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Soil investigation at OHR site and construction of 450cum OHR at Zone-1 for Augmentation of Birpara PWSS under Alipurduar Divisionof North Bengal Circle-I, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000459/2023-2024 | 495/ALD | 16/02/2024 | 23/09/2025 | KAMALESH ROY | 120.29 | 58.79 | 48.87 | 10
32 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Fabrication,Erection of Signage (268 nos) of Pump house/OHR site democration with in Kumargram, Falakata,Madarihat-Birpara Block for Different PWSS of JJM Project Under Alipurduar Division P.H.E.Dte. | HQ-A.E | RWS Kumargram Block | ORD/000354/2024-2025 | 3520/ALD | 04/10/2024 | 30/08/2025 | LIMRA SOCIAL WELFARE SOCIETY | 31.26 | 7.09 | 22.69 | 92
33 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Cons. of pump house, boundary wall and Rising Main for Zone-II 4thTube well site at Aug. of Birpara PWSS of Birpara Sub-Division under Alipurduar Division, PHE Dte. (SM/14233) | Birpara A.E | Birpara Sub Division | ORD/000531/2023-2024 | 850/ALD | 14/03/2024 | 09/03/2025 | RATAN DUTTA | 18.26 | 3.06 | 16.79 | 65
34 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer ,Birpara Sub- Division ,P.H.E. Dte..(from 01.04.2024 to 01.03.2025) | Birpara A.E | Birpara Sub Division | ORD/000538/2023-2024 | 893/ALD | 15/03/2024 | 15/03/2025 | PARITOSH SUTRADHAR | 4.8 | 4.78 | 99.64 | 0
35 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Protective and Decorative Acrylic exterior paint on existing 350 cum OHR at Birpara of Birpara Sub-Division under Alipurduar Division, P.H.E.Dte. (SM/14233) | Birpara A.E | RWS Falakata Block | ORD/000506/2023-2024 | 824/ALD | 14/03/2024 | 13/05/2024 | BHAGWATI BHUJEL | 1.96 | 1.95 | 99.38 | 10
36 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Sinking of Big dia. Tubewell (200 x 150 mm dia.)by modified DTH -ODEX method of drilling at Paschim Khairbari PWSS(SM/10672) and Birpara PWSS Zone-II, 4th TW site(SM/14233)of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Birpara A.E | JUNIOR ENGINEER | ORD/000493/2023-2024 | 749/ALD | 12/03/2024 | 25/07/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 33.26 | 25.29 | 76.04 | 50
37 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 138/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 61.13 | 0 | 0 | 0
38 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2024-2025 | 3980/ALD | 27/11/2024 | 27/11/2024 | Resource Division | 30.8 | 0 | 0 | 0
39 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR AUGUMENTATION OF BIRPARA ZONE-I P/HNO-I |  |  | BILL/03019/2023-2024 | BP-2023-24-696 | 14/03/2024 | 14/03/2024 | WBSEDCL | 7.9 | 0 | 0 | 0
40 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR AUGUMENTATION OF BIRPARA Z-II P/HNO-IV |  |  | BILL/03011/2023-2024 | BP-2023-24-688 | 14/03/2024 | 14/03/2024 | WBSEDCL | 6.55 | 0 | 0 | 0
41 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW SERVICE CONNECTION FOR Augumentation of Birpara PWSS ZONE-IIII P/H NO-III |  |  | BILL/02471/2023-2024 | BP-2023-24-572 | 01/02/2024 | 01/02/2024 | WBSEDCL | 12.06 | 0 | 0 | 0
42 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR BIRPARA CIRCUS GROUND ZONE-III, P/H NO-I |  |  | BILL/03018/2023-2024 | BP-2023-24-695 | 14/03/2024 | 14/03/2024 | WBSEDCL | 9.12 | 0 | 0 | 0
43 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR KFC GROUND AUGUMENTATION OF BIRPARA PWSS ZONE-III P/H NO-II |  |  | BILL/02804/2023-2024 | BP-2023-24-644 | 29/02/2024 | 29/02/2024 | WBSEDCL | 7.01 | 0 | 0 | 0
44 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | New Service Connection for Birpara Thana PWSS, Zone-II, P/H No-II |  |  | BILL/02301/2023-2024 | BP-2023-24-618 | 16/02/2024 | 16/02/2024 | WBSEDCL | 3.74 | 0 | 0 | 0
45 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Laying of DI & HDPE Pipe line, Construction of sluice valve chamber, trenchless pipe laying & other works for providing FHTC at Birpara Zone-I Area under Birpara PWSS under Alipurduar Division, PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000412/2024-2025 | 4595/ALD | 03/01/2025 | 16/08/2025 | KAMALESH ROY | 149.76 | 0 | 0 | 1
46 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Laying of DI & HDPE Pipe line, Construction of sluice valve chamber, trenchless pipe laying & other works for providing FHTC AT BIRPARA Zone-II Area under BIRPARA PWSS under Alipurduar Division, PHE Laying of DI & HDPE Pipe line, Construction of sluice valve chamber, trenchless pipe laying & other works for providing FHTC AT BIRPARA Zone-II Area under BIRPARA PWSS under Alipurduar Division, PHE DTE.. | Birpara A.E | Birpara Sub Division | ORD/000001/2025-2026 | 111/ALD | 16/04/2025 | 31/05/2025 | RATAN DUTTA | 120.16 | 0 | 0 | 0
47 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
48 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Birpara A.E | Birpara Sub Division | ORD/000080/2025-2026 | 1048/ALD | 17/06/2025 | 16/08/2025 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
49 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Supply and installation of sign board at different PWSS under Birpara Sub-Division, under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division,RWS Falakata Block | ORD/000106/2025-2026 | 1224/ALD | 01/07/2025 | 31/07/2025 | DILIP MAHATO (OPC) PRIVATE LIMITED | 6.89 | 0 | 0 | 100
50 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | New Service Connection Charges for New Line Saradapally H.W.C Z-II P/H NO-III Birpara under NMD-II in the dist. of Alipurduar |  |  | BILL/02032/2024-2025 | BP-458/24-25 | 09/01/2025 | 09/01/2025 | WBSEDCL | 15.17 | 0 | 0 | 0
Total | [13 empty] | 2275.6 | 745.73 | 32.77