## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , Soil investigation at OHR site, constructions of 350 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Paschim Deogaon PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000173/2023-2024 | 1047/ALD | 20/07/2023 | 14/07/2024 | SOUVIK ROY PALADHI | 547.06 | 105.37 | 19.26 | 26
2 | ALIPURDUAR | Falakata | Northern Mechanical Division II | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Paschim Deogaon Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000892/2023-2024 | 2477/NMD-II | 11/08/2023 | 10/09/2023 | SUNLIT | 21.78 | 0 | 0 | 50
3 | ALIPURDUAR | Falakata | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Gap filling in main and branch road of Nabanagar area by HDPE/DI pipe as required under Pashchim Deogaon PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000365/2023-2024 | 81/ALD | 10/01/2024 | 09/04/2024 | SOUVIK ROY PALADHI | 38.2 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Laying of DI & HDPE pipeline, construction of sluice valve chamber, trenchless pipe, laying & other works for providing FHTC at Paschim deogaon PWSS under Birpara Sub-Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000350/2024-2025 | 3420/ALD | 26/09/2024 | 25/11/2024 | SOUVIK ROY PALADHI | 35.92 | 0 | 0 | 0
5 | ALIPURDUAR | Falakata | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Supply of CI Sluice Valve and Special and CI Jeffy Coupling for Paschim Deogaon Water Supply Scheme(SM/15207) of Falakata Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000529/2023-2024 | 848/ALD | 14/03/2024 | 12/06/2024 | SOUVIK ROY PALADHI | 18.86 | 0 | 0 | 90
6 | ALIPURDUAR | Falakata | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 187/ALD | 28/04/2023 |  | Resource Division | 24.01 | 0 | 0 | 0
7 | ALIPURDUAR | Falakata | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 121/ALD | 10/01/2024 |  | Resource Division | 12.92 | 0 | 0 | 0
8 | ALIPURDUAR | Falakata | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Material Requisition To Resource Division |  |  | RTOR000027/2024-2025 | 3985/ALD | 27/11/2024 |  | Resource Division | 12.92 | 0 | 0 | 0
9 | ALIPURDUAR | Falakata | Northern Mechanical Division II | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | NEW SERVICE CONNECTION CHARGES AT PASCHIM DEOGAON PWSS TW NO- I IN THE DIST OF ALIPURDUAR. |  |  | BILL/00631/2024-2025 | BP-171/24-25 | 03/07/2024 |  | WBSEDCL | 6.77 | 0 | 0 | null
10 | ALIPURDUAR | Falakata | Northern Mechanical Division II | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | NEW SERVICE CONNECTION CHARGES AT PASCHIM DEOGAON PWSS TW NO- I IN THE DIST OF ALIPURDUAR. |  |  | BILL/00631/2024-2025 | BP-171/24-25 | 03/07/2024 |  | WBSEDCL | 6.77 | 0 | 0 | null
11 | ALIPURDUAR | Falakata | Northern Mechanical Division II | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | New Service Connection Charges for Paschim Deogaon PWSS, P/H-II under NMD-II |  |  | BILL/01897/2024-2025 | BP-436/24-25 | 16/12/2024 |  | WBSEDCL | 2.53 | 0 | 0 | null
Total | [13 empty] | 727.74 | 105.37 | 14.48