## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 187/ALD | 28/04/2023 | 28/04/2023 | Resource Division | 24.01 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Gap filling in main and branch road of Nabanagar area by HDPE/DI pipe as required under Pashchim Deogaon PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000365/2023-2024 | 81/ALD | 10/01/2024 | 09/04/2024 | SOUVIK ROY PALADHI | 38.2 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Laying of DI & HDPE pipeline, construction of sluice valve chamber, trenchless pipe, laying & other works for providing FHTC at Paschim deogaon PWSS under Birpara Sub-Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000350/2024-2025 | 3420/ALD | 26/09/2024 | 25/11/2024 | SOUVIK ROY PALADHI | 35.92 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Supply of CI Sluice Valve and Special and CI Jeffy Coupling for Paschim Deogaon Water Supply Scheme(SM/15207) of Falakata Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000529/2023-2024 | 848/ALD | 14/03/2024 | 12/06/2024 | SOUVIK ROY PALADHI | 18.86 | 0 | 0 | 90
5 | ALIPURDUAR | Falakata | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 121/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 12.92 | 0 | 0 | 0
6 | ALIPURDUAR | Falakata | Alipurduar Division | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Material Requisition To Resource Division |  |  | RTOR000027/2024-2025 | 3985/ALD | 27/11/2024 | 27/11/2024 | Resource Division | 12.92 | 0 | 0 | 0
7 | ALIPURDUAR | Falakata | Northern Mechanical Division II | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | New Service Connection Charges for Paschim Deogaon PWSS, P/H-II under NMD-II |  |  | BILL/01897/2024-2025 | BP-436/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 2.53 | 0 | 0 | 0
8 | ALIPURDUAR | Falakata | Northern Mechanical Division II | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | NEW SERVICE CONNECTION CHARGES AT PASCHIM DEOGAON PWSS TW NO- I IN THE DIST OF ALIPURDUAR. |  |  | BILL/00631/2024-2025 | BP-171/24-25 | 03/07/2024 | 03/07/2024 | WBSEDCL | 6.77 | 0 | 0 | 0
9 | ALIPURDUAR | Falakata | Northern Mechanical Division II | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Paschim Deogaon Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000892/2023-2024 | 2477/NMD-II | 11/08/2023 | 10/09/2023 | SUNLIT | 21.78 | 0 | 0 | 50
10 | ALIPURDUAR | Falakata | Northern Mechanical Division II | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM DEOGAON and others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000169/2025-2026 | 1385/NMD-II | 26/06/2025 | 26/07/2025 | M/S SAJAHAN CHOWDHURY | 20.56 | 0 | 0 | 0
11 | ALIPURDUAR | Falakata | Northern Mechanical Division II | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000134/2025-2026 | 1344/NMD-II | 19/06/2025 | 17/09/2025 | M/S SAJAHAN CHOWDHURY | 42.58 | 0 | 0 | 0
12 | ALIPURDUAR | Falakata | Northern Mechanical Division II | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
Total | [13 empty] | 963.2 | 0 | 0