## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Dhanirampur Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000899/2023-2024 | 2473/NMD-II | 11/08/2023 | 10/09/2023 | SARKAR ELECTRIC | 21.08 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata | Alipurduar Division | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 119/ALD | 10/01/2024 |  | Resource Division | 9.56 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Alipurduar Division | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | Laying of rising main, delivery main, bypass arrangement, Laying of HDPE Pipeline for left out household connection and other allied works at Dhanirampur PWSS (both H/W and 2nd site) of Birpara Sub-Division under Alipurduar Division, P.H.E. Dte. (SM/15208) | Birpara A.E | RWS Falakata Block | ORD/000511/2023-2024 | 829/ALD | 14/03/2024 | 28/04/2024 | DILIP MAHATO | 58.7 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Alipurduar Division | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , Soil investigation at OHR site, constructions of 250 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for DHANIRAMPUR PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000575/2022-2023 | 3636/ALD | 31/03/2023 | 27/09/2023 | DILIP MAHATO | 457.51 | 247.91 | 54.19 | 80
5 | ALIPURDUAR | Falakata | Alipurduar Division | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | Supply of DIDF pipes and DI specials and CI Jeffy Coupling for Dhanirampur Water Supply Scheme (SM/15208) of Falakata Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000519/2023-2024 | 838/ALD | 14/03/2024 | 13/04/2024 | BARMAN ENTERPRISE | 9.78 | 4.89 | 50 | 90
6 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | NEW SERVICE CONNECTION CHARGE DHANIRAMPUR PH NO-II |  |  | BILL/03016/2023-2024 | BP-2023-24-693 | 14/03/2024 |  | WBSEDCL | 5.85 | 0 | 0 | null
7 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | NEW SERVICE CONNECTION CHARGES FOR DHANIRAMPURPH NO-I |  |  | BILL/03014/2023-2024 | BP-2023-24-691 | 14/03/2024 |  | WBSEDCL | 4.08 | 0 | 0 | null
8 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | NEW SERVICE CONNECTION CHARGES FOR DHANIRAMPURPH NO-I |  |  | BILL/03014/2023-2024 | BP-2023-24-691 | 14/03/2024 |  | WBSEDCL | 4.08 | 0 | 0 | null
Total | [13 empty] | 570.63 | 252.8 | 44.3