## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. | SM/15209 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR HANTUPARA P/H NO-IV PWSS |  |  | BILL/02451/2023-2024 | BP-2023-24-551 | 18/01/2024 | 18/01/2024 | WBSEDCL | 5.27 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. | SM/15209 | Augmentation | Renovation of Pump house and boundary wall at H/W site of Hantapara TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000088/2025-2026 | 1172/ALD | 26/06/2025 | 24/09/2025 | MANI PRADHAN | 1.28 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. | SM/15209 | Augmentation | Renovation of Pump house and boundary wall at 2nd site of Hantapara TG PWSS under Alipurduar Division, PHE Dte | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000089/2025-2026 | 1173/ALD | 26/06/2025 | 24/09/2025 | MANI PRADHAN | 1.07 | 0 | 0 | 0
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. | SM/15209 | Augmentation | Renovation of Pump house and boundary wall at 3rd site of Hantapara TG PWSS under Alipurduar Division, PHE Dte | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000090/2025-2026 | 1174/ALD | 26/06/2025 | 24/09/2025 | MANI PRADHAN | 1.05 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. | SM/15209 | Augmentation | Boring of TW, Construction of Pumphouse, Boundary wall, Laying of Distribution system for Augmentation of Hantupara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000517/2022-2023 | 3317/ALD | 13/03/2023 | 18/10/2024 | DULAL DAS | 23.8 | 20.28 | 85.2 | 98
6 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. | SM/15209 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of HANTUPARA water supply scheme, TW no- I Under JJM under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/002039/2023-2024 | 1187/NMD-II | 11/03/2024 | 02/12/2024 | DEY ENTERPRISE (MALDA) | 11.26 | 11.21 | 99.64 | 100
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. | SM/15209 | Augmentation | New Service Connection Charges for Hantapara TG Near GP under NMD-II in the dist of Alipurduar |  |  | BILL/00505/2024-2025 | 330/24-25/PFMS | 18/02/2025 | 18/02/2025 | WBSEDCL | 5.71 | 0 | 0 | 0
Total | [13 empty] | 49.43 | 31.49 | 63.71