## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | Providing balance FHTC for CHALNIPAK PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Madarihat - Birpara Block | ORD/000214/2023-2024 | 1568/ALD | 23/08/2023 | 07/10/2023 | SOUVIK ROY PALADHI | 9.97 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 224/ALD | 03/05/2023 | 03/05/2023 | Resource Division | 13.14 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 2399/ALD | 08/11/2023 | 08/11/2023 | Resource Division | 10.15 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | QUOTATION FOR NEW SERVICE CONNECTION AT CHALNIPAK PWSS P/H NO-III |  |  | BILL/01446/2023-2024 | BP-2023-24-286 | 21/08/2023 | 21/08/2023 | WBSEDCL | 5.44 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | NEW SERVICE CONNECTIO CHARGE FOR CHALNIPAK W/S/S P/H NO.2 |  |  | BILL/00596/2023-2024 | BP-2023-24-177 | 15/06/2023 | 15/06/2023 | WBSEDCL | 1.41 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | QUOTATION FOR NEW SERVICE CONNECTION AT CHALNIPAK PWSS P/H NO. I |  |  | BILL/01447/2023-2024 | BP-2023-24-291 | 21/08/2023 | 21/08/2023 | WBSEDCL | 8.12 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | Constructions of pump house and Sinking of 250 mm x 200 mm X 150 mtr Big dia Tubewel at HW site , 2nd site and 3 rd Site Laying of distribution system with UPVC pipeline , Constructions of 200 Cum OHR as per Departmental Design and drawing , including the Soil investigation works providing FHTC and others allied works for Chalnipak PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | JUNIOR ENGINEER | ORD/000472/2022-2023 | 3156/ALD | 22/02/2023 | 11/02/2025 | SOUVIK ROY PALADHI | 481.77 | 0 | 0 | 50
8 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | Supply of CIDF & CISS Pipes and specials for Chalnipak WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division,JUNIOR ENGINEER | ORD/000238/2023-2024 | 1607/ALD | 25/08/2023 | 24/09/2023 | SOUVIK ROY PALADHI | 7.89 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | Supply of CIDF Specials & Jeffy Coupling for Chalnipak (SM/15534) WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000404/2024-2025 | 4540/ALD | 26/12/2024 | 25/01/2025 | SOUVIK ROY PALADHI | 19.94 | 0 | 0 | 0
10 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/ culvert crossing , Land developement works , Constructions of surface drain , pathway and others allied works in connection with the Chalnipak PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/15534) | HQ-A.E | JUNIOR ENGINEER | ORD/000223/2024-2025 | 2276/ALD | 05/08/2024 | 04/10/2024 | SOUVIK ROY PALADHI | 77.22 | 0 | 0 | 0
11 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | ADDITIONAL QUOTATION FOR CHALNIRPAK PH NO-III |  |  | BILL/02960/2023-2024 | BP-06/24-25 | 08/04/2024 | 08/04/2024 | WBSEDCL | 0.38 | 0 | 0 | 0
12 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
13 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte. (From 01.05.2025 to 30.04.2026) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000032/2025-2026 | 420/ALD | 30/04/2025 | 30/04/2026 | MATRI ENTERPRISE | 4.8 | 0 | 0 | 0
14 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte. (from01.05.2025 to 30.04.2026) | HQ-A.E | Birpara Sub Division | ORD/000031/2025-2026 | 419/ALD | 30/04/2025 | 30/04/2026 | APSARI BHOWMICK | 4.8 | 0 | 0 | 0
15 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Alipurduar-II Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000083/2025-2026 | 1051/ALD | 17/06/2025 | 16/08/2025 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
16 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
17 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | Solarization of grid connected pumping installation at different PWSS at Alipurduar -II block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001205/2024-2025 | 819/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
18 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Chalnipak water supply scheme, TW no I,II and III under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000741/2023-2024 | 2287/NMD-II | 31/07/2023 | 30/08/2023 | QUAZI NOZRUL ISLAM | 27.85 | 0 | 0 | 100
Total | [13 empty] | 1520.47 | 0 | 0